## query
Implementation | Project Name | Dev Type | Sprint | Development ID | FSD / Development Name | Stage | Process Area | Sub Process Area | WRICEF Type | ON Hold Reason | Complexity | Priority of Delivery | Rev Track TR number | FSD Link Solman | Functional Owner | Integration Lead | Dev Lead | ABAP Developer | PI Developer | FSD Planned Del Date | FSD Recieved Date | FSD Planned Walkthrough Date | FSD Actual Walkthrough Date | FUT Status | FUT On Hold Reason | Planned FUT Date | Revised FUT Date | Actual FUT Date | FUT Document | FSI | Dev Planned Delivery Date | Dev Revised Delivery Date | Dev Actual Delivery Date | Dev Planned Start Date | Dev Revised Start Date | Dev Actual Start Date | ABAP Planned Delivery Date | ABAP Revised Delivery Date | ABAP Actual Delivery Date | ABAP TSD Document | ABAP Status | ABAP Effort Forecast (hrs) | ABAP Actual Effort (hrs) | PI Planned Delivery Date | PI Revised Delivery Date | PI Actual Delivery Date | PI Status | PI Effort Forecast (hrs) | PI Actual Effort (hrs) | Tech | Comments | User Story | Reviewer Name | Review Status | Item Type | Path
Catalyst | Kirksville Interfaces (Catalyst) | WRICEF |  | IDD009326 | STS_IDD009326_Purchase Order Information to Dream Version | 06 - Dev Completed | STS |  | I |  | Low | 2 - Medium | 255605 |  | Brian Lefler |  | Sudipta Mondal | Akshay Bhapkar | Charan Somapalli |  | 2022-04-21 | 2022-04-21 | [8 empty] | 2022-05-02 |  | 2022-05-02 | 2022-04-22 |  | 2022-04-22 | 2022-05-02 |  | 2022-05-02 |  | 06 - Dev Completed | 45 | 45 | 2022-05-02 |  | 2022-05-02 | 06 - Dev Completed | 45 | 45 | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Catalyst | Catalyst AP Optimization (Catalyst) | WRICEF |  | EDD3504 | RTR_EDD3504_Automation- Leavers Process | 06 - Dev Completed | RTR |  | E |  | Medium | 2 - Medium | 255893 |  | Nimmi George |  | Sudipta Mondal | Sivakrishna Nichenametla |  |  | 2022-05-19 | 2022-05-19 | [8 empty] | 2022-05-31 |  | 2022-05-31 | 2022-05-19 |  | 2022-05-19 | 2022-05-31 |  | 2022-05-31 |  | 06 - Dev Completed | 60 | 60 |  | 2022-06-08 |  |  |  |  | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7830 | GMD_WDD7830_Finance_Mass change or file upload process | 06 - Dev Completed | MDM | MDG-F | W |  | Medium | 1 - High |  |  | Neela Madhab |  | Amit Gupta |  |  | 2022-06-24 | 2022-06-24 | 2022-07-01 | 2022-07-04 | 02 - FUT Complete |  | 2022-08-08 |  | 2022-08-09 |  | 3.4 | 2022-07-25 |  | 2022-07-25 | 2022-07-18 |  |  | 2022-07-25 | [13 empty] | "05/07/2022 - 1. Initial Mass upload would be taken care by the Data Load team. They would be taking care of all the templates and hierarchy maintenance. They would also be responsible for the validation of the data load. 2. DMO Workflow role would be configured and updated accordingly in the FSD by the Functional owner. 3.Custom BRF+ configuration needs to be done for 0G_ALL to accommodate all the Finance CR types (PC / CC / GL). 4. MDG Email Notification Framework may/may not be required for this FSD. Functional Owner to confirm and update accordingly in the FSD. 5. Business Process Testing would be carried out by the Data Load team once, configurations are done and initial Data load is completed. 6. For testing purpose, requested a sample template from Functional Owner. 06/07/2022 - Check the config of the workflow end to end. Check with Neela for sample data in MDGF. 07/07/2022 - No updates 14/07/2022 - Work in progress in MDG Dev system. 18/07/2022 - Edition creation is pending. Roles creation is pending from security team. Check with Suparno. 20/07/2022 - Development team task/effort is completed." |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | RDD7739 | GMD_RDD7739_Enhance standard process analytics to include Finance master data | 13 - Deferred | MDM | MDG-F | R |  | High |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-08-16 | 2022-08-30 |  |  | 00 - FUT Not Started | [6 empty] | 2022-09-21 |  |  | 2022-08-01 |  |  | 2022-09-21 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7832 | ANZ_MDG_WDD7832_GL_Workflow set up Process | 06 - Dev Completed | MDM | MDG-F | W |  | Medium |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-24 | 2022-06-24 |  |  | 02 - FUT Complete |  | 2022-09-09 | 2022-09-26 | 2022-09-23 |  |  | 2022-08-26 |  | 2022-08-24 | 2022-08-05 |  |  | 2022-08-26 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550067 | GMD_IDD550067_FD_GL MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-F | I |  | High | 1 - High |  |  | Neela Madhab |  |  | Suparno/Debayan |  | 2022-06-17 | 2022-06-17 | 2022-07-01 | 2022-07-01 | 02 - FUT Complete |  | 2022-08-19 |  | 2022-08-09 |  | 3.67 | 2022-07-29 | 2022-08-12 | 2022-08-08 | 2022-07-21 |  |  | 2022-07-29 | [13 empty] | PM:01/08/2022: All standard web service configurations are in place but interfaces working intermittently. Standard monitoring tools showing no errors. SAP OOS message needs to be raised to SAP. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7829 | GMD_WDD7829_FD_Group Account Workflow | 06 - Dev Completed | MDM | MDG-F | W |  | Medium |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-01 |  |  | 02 - FUT Complete |  | 2022-09-01 | 2022-09-26 | 2022-09-20 |  |  | 2022-08-25 |  | 2022-08-24 | 2022-08-08 |  |  | 2022-08-25 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7831 | ANZ_MDG_WDD7831_Cost Center_Workflow set up Process | 06 - Dev Completed | MDM | MDG-F | W |  | Medium |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-24 | 2022-06-24 |  |  | 02 - FUT Complete |  | 2022-09-08 | 2022-09-28 | 2022-09-27 |  |  | 2022-09-21 | 2022-09-21 | 2022-09-15 | 2022-08-10 |  |  | 2022-08-25 | 2022-09-09 | [12 empty] | As discussed with RY and functional team workflow routing logic needs to be changed as per the new business requirement and pending from functional team to confirm yet. 09/09/2022: RY has provided clarifications on Cost Center Category based routing. FSD needs to be updated by RY/ Neela |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7833 | ANZ_MDG_WDD7833_Profit Center_Workflow set up Process | 06 - Dev Completed | MDM | MDG-F | W |  | High |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-24 | 2022-06-24 |  |  | 02 - FUT Complete |  | 2022-09-09 | 2022-09-28 | 2022-09-29 |  |  | 2022-09-21 | 2022-09-21 | 2022-09-19 | 2022-08-10 |  |  | 2022-08-26 | 2022-09-09 | [12 empty] | As discussed with RY and functional team workflow routing logic needs to be changed as per the new business requirement and pending from functional team to confirm yet. 09/09/2022: RY has provided clarifications on Profit Center group based routing. FSD yet to be updated. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550068 | GMD_IDD550068_FD_Cost Center MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-F | I |  | High | 1 - High |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-17 | 2022-06-17 | 2022-07-01 | 2022-07-01 | 02 - FUT Complete |  | 2022-08-19 |  | 2022-08-09 |  | 3.67 | 2022-07-29 |  | 2022-08-08 | 2022-07-18 |  |  | 2022-07-29 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550069 | GMD_IDD550069_FD_Profit Center MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-F | I |  | High | 1 - High |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-17 | 2022-06-17 | 2022-07-01 | 2022-07-01 | 02 - FUT Complete |  | 2022-08-19 |  | 2022-08-09 |  | 3.67 | 2022-07-29 |  | 2022-08-08 | 2022-07-18 |  |  | 2022-07-29 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550074 | GMD_IDD550074_FD_Bank Master MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-F | I |  | High | 1 - High |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-06-24 | 2022-06-24 | 2022-07-12 | 2022-07-12 | 02 - FUT Complete |  | 2022-08-19 |  | 2022-08-09 |  | 3.67 | 2022-07-29 |  | 2022-07-29 | 2022-07-18 |  |  | 2022-07-29 | [13 empty] | It is decided that bank master will be created and maintained in MDG system only. So we need to synch the bank master data with S4 system by an outbound interface. ------------------------------------------------------------------- "05/07/2022 - Port are not yet open and awaiting for updates. 14/07/2022 - Work in progress in MDG Dev system. 18/07/2022 - Patner profile created in both the Development system (MDG and S4) for outbound and inbound interface with distribution system. 20/07/2022 - Development team task/effort is completed." |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550078 | GMD_IDD550078_FD_SOA service replication for BP data distribution | 06 - Dev Completed | MDM | MDG-S | I |  | High | 1 - High |  |  | Mukesh Kumawat |  | Amit Gupta | Suparno/Debayan |  | 2022-06-24 | 2022-06-24 | 2022-07-01 | 2022-07-01 | 02 - FUT Complete |  | 2022-08-05 |  | 2022-08-09 |  | 3.67 | 2022-07-29 | 2022-08-12 | 2022-08-08 | 2022-07-15 |  |  | 2022-07-29 | [13 empty] | PM:01/08/2022: All standard web service configurations are in place but interfaces working intermittently. Standard monitoring tools showing no errors. SAP OOS message needs to be raised to SAP. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7839 | MD_WDD7839_FD_ANZ MDG Vendor Change Process | 06 - Dev Completed | MDM | MDG-S | W |  | Low |  |  |  | Mukesh Kumawat |  | Amit Gupta | Suparno/Debayan |  | 2022-07-08 | 2022-07-13 |  |  | 02 - FUT Complete |  | 2022-09-09 | 2022-09-23 |  |  |  | 2022-09-09 |  | 2022-09-09 | 2022-08-18 |  |  | 2022-09-02 | [13 empty] | 05/09/2022: Dev is on hold due to TR blocking issue due to changes being done by AMS team |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7838 | MD_WDD7838_FD_ANZ MDG Vendor Create workflow | 06 - Dev Completed | MDM | MDG-S | W |  | High |  |  |  | Mukesh Kumawat |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-01 |  |  | 02 - FUT Complete | ​A defect #2 is identified in Vendor create Workflow same is being reported & explained to Dev team Defect can be refer at location : Project Goldilocks - FUT Defect Tracker - All Items (sharepoint.com) | 2022-09-23 |  | 2022-09-20 |  |  | 2022-09-16 |  | 2022-09-05 | 2022-08-18 |  |  | 2022-09-16 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7840 | GMD_WDD7840_FD_Customer Create Workflow | 06 - Dev Completed | MDM | MDG-C | W |  | Very High |  |  |  | Gourav Soni |  | Amit Gupta | Giddaiah/Vidyasagar Reddy |  | 2022-07-01 | 2022-06-24 |  |  | 00 - FUT Not Started |  | 2022-09-19 | 2022-09-30 |  |  |  | 2022-08-31 | 2022-08-31 |  | 2022-07-25 |  |  | 2022-08-31 | [13 empty] | "This will be only process change. The WRICEF document will be updated. There will be no changes in the configuration or ABAP logic." |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7811 | GMD_WDD7811_Customer Update Workflow | 06 - Dev Completed | MDM | MDG-C | W |  | Low |  |  |  | Gaurav Soni |  | Amit Gupta | Giddaiah/Vidyasagar Reddy |  | 2022-06-24 | 2022-06-24 |  |  | 02 - FUT Complete |  | 2022-09-09 | 2022-09-30 | 2022-09-30 |  |  | 2022-08-31 |  | 2022-09-09 | 2022-07-25 |  |  | 2022-08-31 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7856 | GMD_EDD7856_FD_MDG_Finance_Profit Center_Business rules | 06 - Dev Completed | MDM | MDG-F | E |  | High |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-01 | 2022-07-11 | 2022-07-11 | 02 - FUT Complete |  | 2022-09-23 |  | 2022-09-21 |  |  | 2022-09-02 |  | 2022-08-18 | 2022-08-04 |  |  | 2022-09-02 | [12 empty] | MDG Business Rules | 11-07-22: Discussed the FS and testing the Validation and Derivation rules in MWX(Sandbox system). 08-07-22: have scheduled a walkthrough for the FSD on 11th July |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7854 | GMD_EDD7854_FD_MDG_Finance_Cost Center_Business rules | 06 - Dev Completed | MDM | MDG-F | E |  | High |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-01 | 2022-07-11 | 2022-07-11 | 02 - FUT Complete |  | 2022-09-26 |  | 2022-09-19 |  |  | 2022-09-05 |  | 2022-08-18 | 2022-08-04 |  |  | 2022-09-05 | [12 empty] | MDG Business Rules | 11-07-22: Discussed the FS and testing the Validation and Derivation rules in MWX(Sandbox system). 08-07-22: Scheduled a walkthrough of the FSD on 11th July. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7855 | GMD_EDD7855_FD_MDG_Finance_GL_Business rules | 06 - Dev Completed | MDM | MDG-F | E |  | High |  |  |  | Neela Madhab |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-01 | 2022-07-11 | 2022-07-11 | 02 - FUT Complete |  | 2022-09-26 |  | 2022-09-22 |  |  | 2022-09-05 |  | 2022-08-18 | 2022-08-04 |  |  | 2022-09-05 | [12 empty] | MDG Business Rules | 11-07-22: Discussed the FS and testing the Validation and Derivation rules in MWX(Sandbox system). 08-07-22: Scheduled a walkthrough of the FSD on 11th July. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7858 | GMD_EDD7858_ANZ_MDG_Vendor Default, Validation and Derivation FSD | 06 - Dev Completed | MDM | MDG-S | E |  | Medium |  |  |  | Mukesh Kumawat |  | Amit Gupta | Suparno/Debayan |  | 2022-07-01 | 2022-07-04 |  |  | 00 - FUT Not Started |  | 2022-09-28 |  |  |  |  | 2022-09-21 |  | 2022-09-15 | 2022-08-09 |  |  | 2022-09-21 | [12 empty] | MDG Business Rules |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | RDD7736 | GMD_RDD7736_FD_MDG_Configuration Synchronization Report | 06 - Dev Completed | MDM | MDG-F | R |  | High | 1 - High | 257508 |  | Neela Madhab |  | Amit Gupta |  |  | 2022-07-01 | 2022-07-01 | 2022-07-06 | 2022-07-06 | 03 - FUT On Hold | Report is no working as expected. | 2022-09-30 |  |  |  | 2.96 | 2022-09-21 |  | 2022-09-23 | 2022-08-01 |  |  | 2022-09-21 | [13 empty] | 05/07/2022 - Suparno has scheduled meeting with Neela today. 06/07/2022 - Rajesh Y confirmed to schedule meeting with Pepciso team if any similar report are implemented for our reference and based on that we can proceed further 20/07/2022 - Meeting has been scheduled today from Pepsico team (Deviprasad Mohanty) to proceed further. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7861 | GMD_EDD7861_FD_Customer Business rules - Customer Default and Derivation by Region and account grp | 06 - Dev Completed | MDM | MDG-C | E |  | High |  |  |  | Gourav Soni |  | Amit Gupta | Giddaiah/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 00 - FUT Not Started |  | 2022-09-30 |  |  |  |  | 2022-09-15 |  |  | 2022-07-25 |  |  | 2022-09-06 | [12 empty] | MDG Business Rules |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550079 | GMD_IDD550079_FD_Material Replication MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-M | I |  | High | 1 - High |  | https://heinz365.sharepoint.com/:w:/r/sites/MDG_FinanceProject/Shared%20Documents/General/006%20Development/FUT/Material/Functional%20Unit%20Test%20Material%20Master_Product%20Material-ZFIN%20Material%20Creation%20and%20Replication.docx?d=wcc8c4b2fcb9c4c7f887199ef3740cebc&csf=1&web=1&e=aY5sue | Kedar Jamkhedkar |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-06-24 | 2022-06-24 | 2022-07-05 | 2022-07-06 | 02 - FUT Complete |  | 2022-09-02 |  | 2022-08-25 |  | 3.21 | 2022-08-17 | 2022-08-01 | 2022-08-18 | 2022-07-15 |  |  | 2022-08-01 | [13 empty] | Changed dates due to product hierarchy replication and trying to accommodate with the material replication. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7860 | GMD_EDD7860_Enhancement to update Material master from Agile partner | 06 - Dev Completed | MDM | MDG-M | E |  | Medium | 1 - High |  |  | Gopikrishna Vegivada |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-22 | 2022-07-12 | 2022-07-12 | 03 - FUT On Hold | Program is not working as per requirement, There may be some changes in the requirement. informed to development team as well. | 2022-09-13 | 2022-09-23 | 2022-09-26 |  |  | 2022-08-16 | 2022-08-16 | 2022-08-18 | 2022-07-18 |  |  | 2022-08-01 | [13 empty] | "05/07/2022 - Vidhyasagar/Ashwini scheduled meeting with Gopi. 06/07/2022 - FSD to be received today 08/07/2022 - Walkthrough session is scheduled today. 20/07/2022 - Revised FSD to be received today. Ashwini to schedul a short call with Gopi. 21/07/2022 - Gopi confirmed on the chat that ""Enhancement to update material master from agile partner FS is still pending. we have some other priority tasks which is making us to delay this FS. we will deliver this asap." |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550080 | GMD_IDD550080_FD_Classification replication MDG to Goldilocks | 06 - Dev Completed | MDM | MDG-M | I |  | High | 1 - High |  | https://heinz365.sharepoint.com/:w:/r/sites/MDG_FinanceProject/Shared%20Documents/General/006%20Development/FUT/Material/Functional%20Unit%20Test%20Material%20Master_Product%20Material-ZFIN%20Material%20Creation%20and%20Replication.docx?d=wcc8c4b2fcb9c4c7f887199ef3740cebc&csf=1&web=1&e=aY5sue | Kedar Jamkhedkar |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-06-24 | 2022-06-24 | 2022-07-05 | 2022-07-06 | 02 - FUT Complete |  | 2022-09-02 |  | 2022-08-25 |  | 3.21 | 2022-08-17 | 2022-08-01 | 2022-08-18 | 2022-07-15 |  |  | 2022-08-01 | [13 empty] | Changed dates due to product hierarchy replication and trying to accommodate with the material replication. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7834 | GMD_WDD7834_FD_Create Material Parallel Workflow - FG | 06 - Dev Completed | MDM | MDG-M | W |  | High |  |  |  | Kedar Jamkhedkar |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 03 - FUT On Hold | Defect Raised for Material create process flow Change request is still open after last step approval | 2022-09-23 | 2022-09-30 |  |  |  | 2022-09-02 |  | 2022-09-02 | 2022-08-01 |  |  | 2022-09-02 | [13 empty] | 14/07/2022 - Evaluation is in progress and if everything looks good then we can start from 18/07/2022. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7835 | GMD_WDD7835_FD_Create Material Parallel Workflow - Non FG | 06 - Dev Completed | MDM | MDG-M | W |  | High |  |  |  | Gopikrishna Vegivada |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 03 - FUT On Hold | Defect Raised for Material create process flow Change request is still open after last step approval | 2022-09-28 | 2022-09-30 |  |  |  | 2022-09-07 |  | 2022-09-07 | 2022-08-01 |  |  | 2022-09-07 | [13 empty] | 14/07/2022 - Evaluation is in progress from and if everything look good then we can start from 20/07/2022. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7786 | GMD_EDD7786_Material Business rules - MDG_Material Default and Derivation by Material types | 06 - Dev Completed | MDM | MDG-M | E |  | Medium |  |  |  | Gopikrishna Vegivada |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 03 - FUT On Hold | Derivation is not working as expected | [5 empty] | 2022-09-16 |  |  | 2022-07-29 |  |  | 2022-09-09 | [12 empty] | MDG Business Rules |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7853 | GMD_EDD7853_FD_Extend BP as Customer | 06 - Dev Completed | MDM | MDG-C | W |  | High |  |  |  | Gourav Soni |  | Amit Gupta | Giddaiah/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 00 - FUT Not Started |  | 2022-09-30 |  |  |  |  | 2022-08-31 |  |  | 2022-07-25 |  |  | 2022-08-31 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7837 | GMD_WDD7837_FD_Extend Material Parallel Workflow - Non FG | 06 - Dev Completed | MDM | MDG-M | W |  | High |  |  |  | Gopikrishna Vegivada |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 03 - FUT On Hold | Process flow not working as expected (if its a plant & sales extension it should send to both team to approve the request through Parallel processing) Development will be resume in January 2023. | 2022-09-28 |  |  |  |  | 2022-09-07 |  |  | 2022-08-01 |  |  | 2022-09-02 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550036 | GMD_IDD550036_FD_MDG Agile Interface logic based on ERP system | 06 - Dev Completed | MDM | MDG-M | I |  | Low |  |  |  |  | Subhro De |  |  |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete |  | 2022-09-16 | 2022-09-21 | 2022-09-21 |  |  | 2022-09-02 |  | 2022-09-02 | 2022-08-22 | [9 empty] | 2022-09-02 |  |  | 03 - Waiting for FSD walk-through |  |  | PI | 12-AUG-22:PM:Walk through happened with PI. Some further inputs needed to commence development. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7836 | GMD_WDD7836_FD_Extend Material Parallel Workflow - FG | 06 - Dev Completed | MDM | MDG-M | W |  | High |  |  |  | Gopikrishna Vegivada |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 03 - FUT On Hold | Process flow not working as expected (if its a plant & sales extension it should send to both team to approve the request through Parallel processing) Development will be resume in January 2023. | 2022-09-23 |  |  |  |  | 2022-09-02 | 2022-09-08 | 2022-09-09 | 2022-08-01 |  |  | 2022-09-01 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550082 | GMD_IDD550082_FD_MATQM01 for sending QM related fields MDG to S/4HANA | 06 - Dev Completed | MDM | MDG-M | I |  | High |  |  | https://heinz365.sharepoint.com/:w:/r/sites/MDG_FinanceProject/Shared%20Documents/General/006%20Development/FUT/Material/Functional%20Unit%20Test%20Material%20Master_Product%20Material-ZFIN%20Material%20Creation%20and%20Replication.docx?d=wcc8c4b2fcb9c4c7f887199ef3740cebc&csf=1&web=1&e=aY5sue | Kedar Jamkhedkar |  | Amit Gupta | Ashwini/Vidyasagar Reddy |  | 2022-07-01 | 2022-07-01 |  |  | 02 - FUT Complete |  | 2022-08-19 |  | 2022-08-25 |  |  | 2022-08-17 | 2022-08-01 | 2022-08-18 | 2022-07-15 |  |  | 2022-08-01 | [13 empty] | Changed dates due to product hierarchy replication and trying to accommodate with the material replication. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7814 | GMD_WDD7814_MDG_Customer Expdited Approval Create (DMO Only) | 06 - Dev Completed | MDM | MDG-C | W |  | Medium |  |  |  | Gourav Soni |  |  | Giddaiah/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete |  | 2022-09-15 | 2022-09-22 | 2022-09-19 |  |  | 2022-09-01 |  | 2022-08-31 | 2022-07-26 |  |  | 2022-09-01 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7838 | GMD_EDD7838_MDG_Govern Cust Attr (edit_non-edit) by Role | 06 - Dev Completed | MDM | MDG-C | E |  | Medium | [6 empty] | Giddaiah/Vidyasagar Reddy |  | 2022-07-15 | 2022-07-14 |  |  | 00 - FUT Not Started |  | 2022-09-28 | 2022-09-30 |  |  |  | 2022-09-16 |  | 2022-09-23 | 2022-07-26 |  |  | 2022-08-28 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7813 | GMD_WDD7813_MDG_Customer Mark for Deletion Workflow | 06 - Dev Completed | MDM | MDG-C | W |  | Low |  |  |  | Gourav Soni |  |  | Giddaiah/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete |  | 2022-09-16 | 2022-09-23 | 2022-09-20 |  |  | 2022-09-09 |  | 2022-09-07 | 2022-08-05 |  |  | 2022-09-09 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7812 | GMD_WDD7812_MDG_Customer Block Unblock Workflow | 06 - Dev Completed | MDM | MDG-C | W |  | Low |  |  |  | Gourav Soni |  |  | Giddaiah/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete |  | 2022-09-16 | 2022-09-23 | 2022-09-20 |  |  | 2022-09-09 |  | 2022-09-08 | 2022-08-05 |  |  | 2022-09-09 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7827 | GMD_EDD7827_MDG_Country Spec Fld Reqts/validation in Cust Wrkflw | 06 - Dev Completed | MDM | MDG-C | E |  | Medium |  |  |  | Gourav Soni |  |  | Giddaiah/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete |  | 2022-09-26 |  | 2022-09-22 |  |  | 2022-09-12 |  | 2022-09-20 | 2022-08-05 |  |  | 2022-09-12 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7816 | GMD_EDD7816_MDG_Customer Email notifications per workflow | 06 - Dev Completed | MDM | MDG-C | E |  | Medium |  |  |  | Gourav Soni |  |  | Ashwini/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-14 |  |  | 03 - FUT On Hold | Unable to see email notification for customer master in SOST | 2022-09-30 |  |  |  |  | 2022-09-20 |  |  | 2022-08-01 |  |  | 2022-09-20 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7823 | GMD_EDD7823_MDG_Security Roles supporting Customer Workflows | 15 - No Development Required | MDM | MDG-C | E |  | Low | [6 empty] | Ashwini/Vidyasagar Reddy |  | 2022-07-15 | 2022-07-08 | [9 empty] | 2022-08-29 |  |  | 2022-07-25 |  |  | 2022-08-29 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | RDD7737 | GMD_RDD7737_FD_Enhance standard process analytics to include BP master data | 13 - Deferred | MDM | MDG-C | R |  | Medium | [6 empty] | Ashwini/Vidyasagar Reddy |  | 2022-08-05 | 2022-08-30 |  |  | 00 - FUT Not Started | [6 empty] | 2022-09-21 |  |  | 2022-08-01 |  |  | 2022-09-21 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7841 | GMD_WDD7841_ANZ_MDG_Extend BP as Vendor Workflow process | 06 - Dev Completed | MDM | MDG-S | W |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-08-05 | 2022-08-01 |  |  | 02 - FUT Complete | Requested Dev team to look and configure the CR Status for every each approval , revision and reject step. | 2022-09-23 |  | 2022-09-21 |  |  | 2022-09-09 |  | 2022-09-09 | 2022-08-16 |  |  | 2022-09-09 | [13 empty] | 05/09/2022: Functional Owner has to update the FSD with correct Workflow Logic |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7862 | GMD_EDD7862_ANZ_MDG_Vendor_BP data model enhancement | 06 - Dev Completed | MDM | MDG-S | E |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-07-08 | 2022-07-08 |  |  | 02 - FUT Complete | ​ ​A defect #2 is identified in Vendor create Workflow same is being reported & explained to Dev team Defect can be refer at location : Project Goldilocks - FUT Defect Tracker - All Items (sharepoint.com) | 2022-09-23 |  | 2022-09-22 |  |  | 2022-09-09 |  | 2022-08-18 | 2022-08-11 |  |  | 2022-09-09 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7822 | GMD_EDD7822_Maint governance For Vendor Attributes by Role | 06 - Dev Completed | MDM | MDG-S | E |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-08-05 | 2022-08-04 |  |  | 00 - FUT Not Started |  | 2022-09-30 |  |  |  |  | 2022-09-21 |  |  | 2022-07-22 |  |  | 2022-08-26 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7821 | GMD_EDD7821_MDG_Security Roles supporting the Vendor Workflows | 15 - No Development Required | MDM | MDG-S | E |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-08-05 | [10 empty] | 2022-08-26 |  |  | 2022-07-22 |  |  | 2022-08-26 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7807 | MDG_Vendor Block/Unblock Workflow process in MDG | 06 - Dev Completed | MDM | MDG-S | W |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-07-08 | 2022-07-13 |  |  | 02 - FUT Complete |  | 2022-09-30 |  | 2022-09-23 |  |  | 2022-09-16 |  | 2022-09-09 | 2022-08-25 |  |  | 2022-09-16 | [13 empty] | 05/09/2022: Dev is on hold due to TR blocking issue due to changes being done by AMS team |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7815 | GMD_EDD7815_MDG_Vendor Email notifications per workflow | 06 - Dev Completed | MDM | MDG-S | E |  | Medium | [6 empty] | Suparno/Debayan |  | 2022-07-15 |  | 2022-07-05 | 2022-07-07 | 00 - FUT Not Started |  | 2022-09-30 |  |  |  |  | 2022-09-21 |  |  | 2022-08-25 |  |  | 2022-09-21 | [13 empty] | 08/07/2022 - Waiting for inputs from Pramod |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | WDD7809 | MDG_Vendor Mark for Deletion Process in MDG | 06 - Dev Completed | MDM | MDG-S | W |  | Low | [6 empty] | Suparno/Debayan |  | 2022-07-08 |  |  |  | 02 - FUT Complete |  | 2022-09-30 |  | 2022-09-26 |  |  | 2022-09-20 |  | 2022-09-09 | 2022-08-25 |  |  | 2022-09-20 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | RDD7738 | GMD_RDD7738_FD_Enhance standard process analytics to include material master data | 13 - Deferred | MDM | MDG-M | R |  | High | [6 empty] | Ashwini/Vidyasagar Reddy |  | 2022-07-08 | 2022-08-30 |  |  | 00 - FUT Not Started | [6 empty] | 2022-09-21 |  |  | 2022-08-01 |  |  | 2022-09-21 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | NA | DMO Approval for Material | 14 - Out of scope | MDM | MDG-M | W |  | Low |  |  |  | Gopi |  |  | Ashwini/Vidyasagar Reddy |  | 2022-07-08 | [10 empty] | 2022-09-05 |  |  | 2022-08-05 |  |  | 2022-09-05 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7859 | GMD_EDD7859_FD_MDG Enhancement for Email notifications as per the workflow | 06 - Dev Completed | MDM | MDG-M | E |  | Medium | [6 empty] | Ashwini/Vidyasagar Reddy |  | 2022-07-08 | 2022-07-08 |  |  | 03 - FUT On Hold | FUT is dependent on Material Create workflow, Defect is raised for material create process flow.Once that will be fix we can do FUT. | 2022-09-30 |  |  |  |  | 2022-09-21 |  |  | 2022-08-05 |  |  | 2022-09-21 | [17 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_F_001 | PTM_F_001 _ PM Shop Paper Printing of work orders v0.1 | 06 - Dev Completed | PTM |  | F |  | Low | 3 - Low |  |  | Lorena Acilo |  | Pratik Mallick | Swapnali Rasal |  | 2022-07-01 | 2022-07-04 | 2022-07-04 | 2022-07-04 | [6 empty] | 4.04 | 2022-07-13 |  | 2022-07-13 | 2022-07-05 |  | 2022-07-05 | 2022-07-13 |  | 2022-07-13 |  | 06 - Dev Completed | 45 | 45 | [6 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTP_F_001 | PTP_F_001_PO Output | 15 - No Development Required | PTP |  | F |  | Medium | 3 - Low |  |  | Pavan Kannan |  | Pratik Mallick | Shramana Hazra |  |  | 2022-07-06 | 2022-07-07 | 2022-07-07 | [6 empty] | 3.72 | 2022-08-03 |  |  | 2022-07-13 |  | 2022-07-13 | 2022-08-03 |  |  |  | 04 - Dev in progress | 135 | [7 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTP_F_018 | PTP_18_Print delivery schedules | 04 - Dev in progress | PTP |  | F |  | Medium | 3 - Low |  |  | Pavan Kannan |  | Pratik Mallick | Mehedi Das Gupta |  |  | 2022-07-06 | 2022-07-07 | 2022-07-07 | [6 empty] | 3.52 | 2022-08-03 |  |  | 2022-07-13 |  | 2022-07-13 | 2022-08-03 |  |  |  | 04 - Dev in progress | 135 | [7 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_E_003 | LE_EDD003_Index Table for Fuel Surcharge Calculation | 04 - Dev in progress | LEX |  | E |  | Medium | 2 - Medium |  |  | Aneet Singh Chadha |  | Pratik Mallick | Sankharupa Saha |  |  | 2022-07-05 | 2022-07-06 | 2022-07-06 | [6 empty] | 3.56 | 2022-08-03 |  |  | 2022-07-13 |  | 2022-07-15 | 2022-08-03 |  |  |  | 04 - Dev in progress | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | OTC_E_001 | OTC_EDD001_PH Data Dictionary | 06 - Dev Completed | OTC |  | E |  | Low | 1 - High |  |  | Syed Saad |  | Pratik Mallick | Sneha Ghosh |  |  | 2022-07-06 | 2022-07-06 | 2022-07-06 | [6 empty] | 4.4 | 2022-07-14 |  | 2022-07-13 | 2022-07-07 |  | 2022-07-07 | 2022-07-14 |  | 2022-07-13 |  | 06 - Dev Completed | 45 | 27 | [6 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_022 | LE_IDD022_Send Freight Order Tracking Request to FourKites | 11 - Draft Dev Started | LEX |  | I |  | Medium | 1 - High |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick | Neeraj P Singh | Krati Agarwal |  | 2022-07-04 | 2022-07-06 | 2022-07-06 | [6 empty] | 3.62 | 2022-08-10 |  |  | 2022-07-13 |  |  | 2022-08-10 |  |  |  | 11 - Draft Dev Started |  |  | 2022-08-10 |  |  | 11 - Draft Dev Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_023 | LE_IDD023_Receive Freight Order Events from FourKites | 11 - Draft Dev Started | LEX |  | I |  | High | 1 - High |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick | Sneha Ghosh | Chevva Tirumalesh |  | 2022-07-04 | 2022-07-06 | 2022-07-06 | [6 empty] | 3.52 | 2022-08-10 |  |  | 2022-07-13 |  |  | 2022-08-10 |  |  |  | 11 - Draft Dev Started |  |  | 2022-08-10 |  |  | 11 - Draft Dev Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_026 | LE_IDD026_Send Freight Booking Tracking Request to FourKites | 11 - Draft Dev Started | LEX |  | I |  | Medium | 1 - High |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick | Neeraj P Singh | Krati Agarwal |  | 2022-07-04 | 2022-07-06 | 2022-07-06 | [6 empty] | 3.91 | 2022-08-10 |  |  | 2022-07-13 |  |  | 2022-08-10 |  |  |  | 11 - Draft Dev Started |  |  | 2022-08-10 |  |  | 11 - Draft Dev Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_027 | LE_IDD027_Receive Freight Booking Events from FourKites | 11 - Draft Dev Started | LEX |  | I |  | High | 1 - High |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick | Sneha Ghosh | Chevva Tirumalesh |  | 2022-07-04 | 2022-07-06 | 2022-07-06 | [6 empty] | 3.52 | 2022-08-10 |  |  | 2022-07-13 |  |  | 2022-08-10 |  |  |  | 11 - Draft Dev Started |  |  | 2022-08-10 |  |  | 11 - Draft Dev Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_005 | LE_IDD005_Outbound Delivery Creation (KHC to 3PL) | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Subrat Choudhury | Subhro De | Pratik Mallick |  |  |  | 2022-07-11 | [19 empty] | 02- FSD received / Dev not Started | [5 empty] | 02- FSD received / Dev not Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_006 | LE_IDD006_Outbound Delivery Change (KHC to 3PL) | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Subrat Choudhury | Subhro De | Pratik Mallick |  |  |  | 2022-07-11 | [19 empty] | 02- FSD received / Dev not Started | [5 empty] | 02- FSD received / Dev not Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_007 | LE_IDD007_Pick Confirmation to Goods Issue (3PL to KHC) | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Priscilla Luna | Subhro De | Pratik Mallick |  |  |  | 2022-07-11 | [19 empty] | 02- FSD received / Dev not Started | [5 empty] | 02- FSD received / Dev not Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_031 | LE_IDD031_Transfer posting 3PL to KHC | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Vaibhav Virkud | Subhro De | Pratik Mallick |  |  |  | 2022-07-11 | [19 empty] | 02- FSD received / Dev not Started | [5 empty] | 02- FSD received / Dev not Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_033 | LE_IDD033_Scrapping from 3PL and Paperless to S4 | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Vaibhav Virkud | Subhro De | Pratik Mallick |  |  |  | 2022-07-11 | [19 empty] | 02- FSD received / Dev not Started | [5 empty] | 02- FSD received / Dev not Started |  |  | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_I_001 | PTM_I_001 -IDSNET Palletiser | 12 - FSD Rejected | PTM |  | I |  | Medium |  |  |  | Raj Dhotre | Subhro De | Pratik Mallick |  |  |  | 2022-07-12 | [19 empty] | 12 - FSD Rejected | [5 empty] | 12 - FSD Rejected |  |  | ABAP;#PI | SM (07/21): The FSD is rejected as there are many open questions regarding mapping, integration methodology, etc. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_F_005 | PTM_F_005_Product Non conformance form | 04 - Dev in progress | PTM |  | F |  | Medium |  |  |  | Madhavi Jalari |  | Pratik Mallick | Durgabhavani Kristipati |  |  | 2022-07-13 | 2022-07-14 | 2022-07-14 | [6 empty] | 3.54 | 2022-08-09 |  |  | 2022-07-19 |  | 2022-07-19 | 2022-08-09 |  |  |  | 04 - Dev in progress | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_F_006 | PTM_F_006_Sample Label | 04 - Dev in progress | PTM |  | F |  | Low |  |  |  | Madhavi Jalari |  | Pratik Mallick | Ashish Goudo |  |  | 2022-07-12 | 2022-07-13 | 2022-07-14 | [6 empty] | 3.5 | 2022-08-02 |  |  | 2022-07-19 |  | 2022-07-19 | 2022-08-02 |  |  |  | 04 - Dev in progress | 90 | [7 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_I_006 | PTM_I_006_Blue Yonder_Bill of Material Interface | 12 - FSD Rejected | PTM |  | I |  | Medium |  |  |  | Stuart Lowe | Subhro De | Pratik Mallick |  |  |  | 2022-07-13 | [19 empty] | 12 - FSD Rejected | [5 empty] | 12 - FSD Rejected |  |  | ABAP;#PI | SM (07/21): The FSD is rejected as it doesn't have sufficient details: 1) The target mapping is not yet complete. 2) The FS needs to contain the details on how the data will be integrated with Blue Yonder, e.g. file based, proxy, etc. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_E_004 | PTM_E_004_Batch Number Format | 04 - Dev in progress | PTM |  | E |  | High |  |  |  | Lorena Acilo |  | Pratik Mallick | Mayuri Sangvi |  |  | 2022-07-13 | 2022-07-14 | 2022-07-14 | [6 empty] | 3.67 | 2022-08-18 |  |  | 2022-07-21 |  | 2022-07-21 | 2022-08-18 |  |  |  | 04 - Dev in progress | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_F_002 | PTM_F_002_PP Shop Paper | 04 - Dev in progress | PTM |  | F |  | Medium |  |  |  | Loren Acilo |  | Pratik Mallick | Swapnali Rasal |  |  | 2022-07-13 | 2022-07-14 | 2022-07-14 | [6 empty] | 3.56 | 2022-08-11 |  |  | 2022-07-21 |  | 2022-07-21 | 2022-08-11 |  |  |  | 04 - Dev in progress | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_F_001 | LE_FDD001_Picklist Form | 16 - FS Review in Progress | LEX |  | F |  | Medium |  |  |  | Pavan Kumar Vandagal |  | Pratik Mallick |  |  |  | 2022-07-13 | [28 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_F_002 | LE_FDD002_HU Label | 16 - FS Review in Progress | LEX |  | F |  | Medium |  |  |  | Pavan Kumar Vandagal |  | Pratik Mallick |  |  |  | 2022-07-13 | [28 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_E_014 | LE_EDD014_Picking strategy enhancement for staging | 11 - Draft Dev Started | LEX |  | E |  | High |  |  |  | Pavan Kumar Vandagal |  | Pratik Mallick | Aratrika Banerjee |  |  | 2022-07-13 | 2022-07-18 | 2022-07-18 | [6 empty] | 3.64 |  |  |  | 2022-07-21 |  |  | 2022-08-18 |  |  |  | 11 - Draft Dev Started | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_009 | LE_IDD009_Stock Adjustment (3PL to KHC) | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Vaibhav Virkud | Subhro De | Pratik Mallick |  |  |  | 2022-07-13 | [28 empty] | ABAP;#PI |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_R_003 | PTM_R_003_Stock Report for Quality Notifications | 04 - Dev in progress | PTM |  | R |  | Low |  |  |  | Madhavi Jalari |  | Pratik Mallick | Paramita Bose |  |  | 2022-07-13 | 2022-07-15 | 2022-07-15 | [6 empty] | 3.5 | 2022-08-04 |  |  | 2022-07-21 |  | 2022-07-21 | 2022-08-04 |  |  |  | 04 - Dev in progress | [8 empty] | ABAP |  |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTP_W_002A | PTP_W_002A_Purchase Order Approval Workflow | 16 - FS Review in Progress | PTP |  | W |  | Medium |  |  |  | Jonathan Tauro |  | Pratik Mallick |  |  |  | 2022-07-14 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTP_W_002B | PTP_W_002B_Purchase Requistion Approval Workflow | 16 - FS Review in Progress | PTP |  | W |  | Medium |  |  |  | Jonathan Tauro |  | Pratik Mallick |  |  |  | 2022-07-14 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_016 | RTR_EDD_FIN_E_016_Overhead Template Allocation | 16 - FS Review in Progress | RTR |  | E |  | Low |  |  |  | Teck Choy Lai |  | Pratik Mallick |  |  |  | 2022-07-15 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_005 | RTR_EDD005_Mass Revaluation of Asset Values from File Upload (Fiori App Only) | 16 - FS Review in Progress | RTR |  | E |  | Low |  |  |  | Eros Gideon Acosta (Zeon) |  | Pratik Mallick |  |  |  | 2022-07-15 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_007 | RTR_EDD007_DMEE Bank Payment File - Domestic Australia (HSBC) | 15 - No Development Required | RTR |  | E |  | Low |  |  |  | Elsa Chen |  | Pratik Mallick |  |  |  | 2022-07-15 | [19 empty] | 15 - No ABAP Development | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_008 | RTR_EDD008_DMEE Bank Payment File - Domestic New Zealand (HSBC) | 15 - No Development Required | RTR |  | E |  | Low |  |  |  | Elsa Chen |  | Pratik Mallick |  |  |  | 2022-07-15 | [19 empty] | 15 - No ABAP Development | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_009 | RTR_EDD009_DMEE Bank Payment File - International AU & New Zealand (HSBC)(MT103) | 15 - No Development Required | RTR |  | E |  | Low |  |  |  | Elsa Chen |  | Pratik Mallick |  |  |  | 2022-07-15 | [19 empty] | 15 - No ABAP Development | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_I_027 | RTR_IDD027_BMG Bank Interface - Outbound | 15 - No Development Required | RTR |  | I |  | Medium |  |  |  | Elsa Chen | Subhro De | Pratik Mallick |  |  |  | 2022-07-15 | [19 empty] | 15 - No ABAP Development | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_F_006 | LE_FDD006_Shipping Manifest | 16 - FS Review in Progress | LEX |  | F |  | Medium |  |  |  | Pralhad Deshmukh |  | Pratik Mallick |  |  |  | 2022-07-18 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_F_012 | LE_FDD012_Export Packing List Form_v0.1 | 16 - FS Review in Progress | LEX |  | F |  | Medium |  |  |  | Pralhad Deshmukh |  | Pratik Mallick |  |  |  | 2022-07-18 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_E_004 | LE_EDD004_Collective Order Rate Lookup Enhancement for Collective Freight Settlement | 16 - FS Review in Progress | LEX |  | E |  | Medium |  |  |  | Pralhad Deshmukh |  | Pratik Mallick |  |  |  | 2022-07-19 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_F_010 | LE_FDD010_Export Carters Note Form | 16 - FS Review in Progress | LEX |  | F |  | Medium |  |  |  | Pralhad Deshmukh |  | Pratik Mallick |  |  |  | 2022-07-19 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_E_008 | PTM_E_008_Email functionality in Quality Notification | 16 - FS Review in Progress | PTM |  | E |  | Medium |  |  |  | Madhavi Jalari |  | Pratik Mallick |  |  |  | 2022-07-21 | [19 empty] | 02- FSD received / Dev not Started | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_E_007 | PTM_E_007_Quality Notification Task Email | 16 - FS Review in Progress | PTM |  | E |  | Medium |  |  |  | Madhavi Jalari |  | Pratik Mallick |  |  |  | 2022-07-22 | [19 empty] | 02- FSD received / Dev not Started | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_040 | LE_IDD040_Stock Reconciliation from 3PL to S4 | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick |  |  |  | 2022-07-22 | [19 empty] | 02- FSD received / Dev not Started | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_004 | LE_IDD004_Load Planning File (KHC to 3PL) | 16 - FS Review in Progress | LEX |  | I |  | Medium |  |  |  | Pralhad Deshmukh | Subhro De | Pratik Mallick |  |  |  | 2022-07-22 | [19 empty] | 02- FSD received / Dev not Started | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_E_019 | LE_EDD019__Enhancement for adding extra columns to standard FO Excel Output for Carrier Collaboration for Loadout Sheets | 16 - FS Review in Progress | LEX |  | E |  | High |  |  |  | Aneet Singh Chadha |  | Pratik Mallick |  |  |  | 2022-07-22 | [19 empty] | 02- FSD received / Dev not Started | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_E_006 | PTM_E_006_Auto task assignment in notification | 17- FSD received / FS Review Pending | PTM |  | E |  | Medium |  |  |  | Madhavi Jalari |  | Pratik Mallick | Swetha |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_I_012 | PTM_I_012 _OUT -GEA - RockwellFactory Talk | 17- FSD received / FS Review Pending | PTM |  | I |  | Medium |  |  |  | Raj Dhotre | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | PTM_I_012 | PTM_I_012 _IN -GEA -Rockwell factory Talk | 17- FSD received / FS Review Pending | PTM |  | I |  | Medium |  |  |  | Raj Dhotre | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_E_011 | LE_EDD011_FS_RF for PSA Returns | 17- FSD received / FS Review Pending | LEX |  | E |  | Medium |  |  |  | Pavan Kumar Vandagal |  | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_038 | LE_IDDIE038_FS_Send Putaway WT to Subsystem ( Paperless) | 17- FSD received / FS Review Pending | LEX |  | I |  | Medium |  |  |  | Pavan Kumar Vandagal | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | LE_I_039 | LE_IDDIE039_FS_Confirmation from Paperless to S4 | 17- FSD received / FS Review Pending | LEX |  | I |  | Medium |  |  |  | Pavan Kumar Vandagal | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_I_018 | FIN_I_018_IDD_Demantra to S4HANA - Demantra to S4HANA - Inbound dispute case_V1.0 | 17- FSD received / FS Review Pending | RTR |  | I |  | High |  |  |  | Elsa Chen | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_R_003 | RTR_RDD003_FS_Project System Reports (with Local Currency) (including Fiori Apps) | 17- FSD received / FS Review Pending | RTR |  | R |  | Medium |  |  |  | Elsa Chen |  | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_I_026 | RTR_IDD026_FS_HSBC Bank Interface - Outbound | 17- FSD received / FS Review Pending | RTR |  | I |  | Medium |  |  |  | Elsa Chen | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_I_019 | FIN_I_019_IDD_Demantra to S4HANA - Inbound ARAP Claims (credit memo)_V1.0 | 17- FSD received / FS Review Pending | RTR |  | I |  | Medium |  |  |  | Elsa Chen | Subhro De | Pratik Mallick |  |  |  | 2022-07-25 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP S/4 HANA (Goldilocks) | WRICEF |  | RTR_E_017 | RTR_EDD_FIN_E_017_Mass Upload for Material Planned Price | 16 - FS Review in Progress | RTR |  | E |  | Medium |  |  |  | Eros Gideon Acosta (Zeon) |  | Pratik Mallick |  |  |  | 2022-07-18 | [33 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | EDD7794 | GMD_EDD7794_MDG_MM Data Model Enhancement to include Custom Fields in UIBB | 06 - Dev Completed | MDM | MDG-M | E |  | Medium | [8 empty] | 2022-08-08 | 2022-08-08 |  |  | 03 - FUT On Hold | FUT is dependent on Material Create workflow, Defect is raised for material create process flow.Once that will be fix we can do FUT. | 2022-09-30 |  |  |  |  | 2022-09-14 |  |  | 2022-09-01 | [20 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
Goldilocks (ANZ) | ANZ SAP MDG (Goldilocks) | WRICEF |  | IDD550085 | GMD_IDD550085_MDG Enhancement Load program Data Conversion for Hierarchies | 06 - Dev Completed | MDM | MDG-M | E |  | Medium | 1 - High | 0000256746, 0000257040 | https://heinz365.sharepoint.com/:w:/r/sites/MDG_FinanceProject/Shared%20Documents/General/006%20Development/FUT/Material/Functional%20Unit%20Test%20Material%20Master_Product%20Hierarchy%20Data%20load.docx?d=wf94141a636234db08cf801db415754a1&csf=1&web=1&e=7laA7Z | Gopikrishna Vegivada |  | Pratik Mallick | Pratik Mallick |  | 2022-08-08 |  |  |  | 02 - FUT Complete |  | 2022-09-08 |  | 2022-09-08 |  |  | 2022-08-23 |  | 2022-08-18 | [21 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | Task 1399/User Story 1387 | EWM_GLOBAL_WRICEF ID_FS_TM_Inbound Shipment Create For STO | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint2 | E |  | Medium | [6 empty] | Aratrika Banerjee | [5 empty] | 02 - FUT Complete | [6 empty] | 2022-11-24 | [9 empty] | 06 - Dev Completed |  | 63 | [11 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | Task 386 | EWM_GLOBAL_WRICEF ID_FS_Program Variables Table | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint1 | E |  | Low | [6 empty] | Aratrika Banerjee | [5 empty] | 02 - FUT Complete | [6 empty] | 2022-11-10 | [11 empty] | 42 | [11 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | EWM_NA_WRICEF ID_FS_SCAC Code ID | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint1 | E |  | Medium | [6 empty] | Pranali D Chavat | [5 empty] | 02 - FUT Complete | [6 empty] | 2022-11-21 | [11 empty] | 62 | [11 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | System Setup |  | Task 3446 / User Story 3429 | System Set up | 06 - Dev Completed | LEX |  | C |  | Low | [6 empty] | Pranali Dnayneshwar Chavat | [5 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | System Setup |  | BD10 /BD93 | BD93 BTE enhacement | 06 - Dev Completed | LEX |  | E |  | Medium | 1 - High |  |  | Sanjib Gosh |  |  | Pranali Chavat | [5 empty] | 02 - FUT Complete | [5 empty] | 1 | [10 empty] | 06 - Dev Completed | [7 empty] | 10 | [5 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | Defect |  | Material Mater PSTAT Values | MaterialMater IDOC | 06 - Dev Completed | LEX |  | I |  | Low | 1 - High |  |  | Sanjib Ghosh |  |  | Pranali | [5 empty] | 02 - FUT Complete | [5 empty] | 1 | [10 empty] | 06 - Dev Completed |  | 8 |  |  |  |  | 2 | 2 | [5 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | EWM_GLOBAL_WRICEF ID_FS_Inbound Scheduling Dashboard | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint2 | E |  | High | [6 empty] | Pranali D Chavat |  |  | 2022-11-22 |  |  | 01 - FUT in Progress | [6 empty] | 2022-12-08 |  | 2022-12-08 | [7 empty] | 06 - Dev Completed |  | 81 | [7 empty] | 15-12 : After the Client demo held on 14-12 we need to work on a few more changes. FS to be updated accordingly 09-12 : All FUT issues resolved. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | OB: Delivery integration with customer specific date | 14 - Out of scope | LEX | EWM-NA-Phase1-Sprint2 | E |  | Medium | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | Truckboard | 04 - Dev in progress | EWM | EWM-NA-Phase1-Sprint2 | E |  | Very High | [6 empty] | Mayuri Sangvi | [5 empty] | 01 - FUT in Progress | [6 empty] | 2022-12-15 |  | 2022-12-15 | [9 empty] | 80 | [7 empty] | 08-01 : Retrofit completed till date. Dev in progress for Phrase II 24-12 : Dev in progress for Phrase II 15-12 : Whatsoever was planned to get delivered in Phrase I has been delivered. After the demo we have some changes that need to be worked on. 02-12 : The Header is completed. Item and function keys are planned to be delivered by this week i.e. 9th Dec 2022 09-12 : The Item level is also completed along with the buttons for display. The functionality is yet to be incorporated. Planned to do it by next week(16-12)Also the defects are being worked on simultaneously with the dev. 28-11 : As it a high complexity object it will be delivered in parts. This is a tentative date planned in which part of the functionality will be delivered. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | ECC open order report | 14 - Out of scope | LEX |  | R |  | Medium | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | TM : Shipment Packing for Means of Transport (OTM to ECC) | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint2 | I |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 01 - FUT in Progress | [6 empty] | 2022-12-09 |  | 2022-12-09 | [9 empty] | 67 | [11 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | System Setup |  | NA | BC Set Activation | 13 - Deferred | LEX | EWM-NA-Phase1-Sprint2 | E |  | Medium | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | MD : Custom Field Integration | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint2 | E |  | Medium | [6 empty] | Abhishek Ganguly | [5 empty] | 00 - FUT Not Started | [6 empty] | 2022-12-13 |  | 2022-12-13 |  |  |  | 2022-12-12 | [5 empty] | 67 | [7 empty] | Design change. New FSD yet not received. 09-12 : New FSD received on 05-12. Dev in progress.Planned to deliver on 12-12. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | TM : Shipment - TU Create Integration (Custom fields) from ECC | 06 - Dev Completed | EWM | EWM-NA-Phase1-Sprint2 | I |  | High | [6 empty] | Aratrika Banerjee | [5 empty] | 00 - FUT Not Started | [6 empty] | 2022-12-13 |  | 2022-12-13 | [9 empty] | 70 | [7 empty] | FSD updated on 01-12 based on the workshop held on 29-11. One of the fields logic yet to be updated. Also there is a new requirement to display the custom TU fields on EWM Monitor. This functionality is yet to be achieved. Hence the ABAP delivery date has been replanned to 05-12-2022. 09-12 : Whatever requirements were given until 07-12 have been delivered along with FUT testing. A new requirement discussed that needs to be walked through with the FO and then dev to start for that. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 1 | WRICEF |  | TBD | OB Delivery integration with customer specific code date | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Sneha Ghosh |  |  |  |  | 2022-12-21 | [7 empty] | 2023-01-06 |  | 2023-01-06 | [7 empty] | 06 - Dev Completed | [13 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | RF : Unloading and Receiving | 04 - Dev in progress | EWM |  | E |  | Very High |  | 0000259330 |  | Lauren DeLuca |  |  | Pranali D Chavat |  | 2023-01-05 | 2023-01-05 | 2023-01-09 | 2023-01-09 | 00 - FUT Not Started | [6 empty] | 2023-02-01 | [10 empty] | 110 | [7 empty] | ABAP | 24-01 : All demo specific requirements were delivered. Working on the rest of the FSD 06-01 : FS walkthrough planned on 09-01-2023 16-01 : FS split into two parts. Some of the functionalities will be completed by 19th and its planned to be a part of the demo scheduled on 24th Jan 2023. |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | RF_Putaway Execution | 04 - Dev in progress | EWM |  | E |  | Medium |  | 0000259355 |  | Lauren DeLuca |  |  | Aratrika Banerjee |  | 2023-01-05 | 2023-01-05 | 2023-01-09 | 2023-01-12 | 00 - FUT Not Started | [6 empty] | 2023-01-30 | [18 empty] | ABAP | 24-01 : Demo specific requirements were delivered. Rest will be done by 30th 12-01 : FSD walkthrough planned on 12-01 16-01 : For demo purpose few functionlaities will be delivered by 18th january 2023 |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | Putaway Strategy | 04 - Dev in progress | EWM |  | E |  | High | [6 empty] | Mayuri Sangvi |  | 2023-01-05 | 2023-01-05 | 2023-01-09 | 2023-01-09 | 00 - FUT Not Started | [6 empty] | 2023-01-19 |  | 2023-01-19 |  |  |  |  | 2023-01-20 |  |  |  | 55 | [7 empty] | ABAP | 24-01: Putaway Capacity Calculation - DONE Putaway SLED Mixing - Changes might come up later based on further testing 06-01: Walkthrough planned on 09-01 12-01: Dev in progress 16-01: Planned to deliver on 19th January 2023 on a priority basis for the demo |  |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | YM : Custom Fields Capture | 06 - Dev Completed | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | YM : Linking Physical trailer - Shipment TU | 01- FSD not received | EWM |  | E |  | Low | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 2 | WRICEF |  | NA | TM : Shipment creation for ABS/Custom Fields Update to ECC | 01- FSD not received | EWM |  | I |  | Medium | [12 empty] | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0011 | Outbound Truckboard : Item level- Warehouse Order/Warehouse Task view | 06 - Dev Completed | EWM |  | E |  | Low |  | 0000262972 |  | Tharonie Kotha |  | Pratik Malick | Mrudula NC |  |  | 2023-08-08 | 2023-08-10 | 2023-08-10 | 01 - FUT in Progress | [6 empty] | 2023-08-11 |  | 2023-08-11 | 2023-08-10 | 2023-08-10 |  | 2023-08-11 |  | 2023-08-11 |  |  | 15 | 15 | [9 empty] | Pratik Mallick |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0003 | Material Master Custom Fields Integration - Alt UoM DS failed in idoc | 06 - Dev Completed | EWM |  | E |  | Low |  | 263071 |  | Jameel Hussain |  | Pratik Mallick | Pranali Chavat |  |  | 2023-08-11 |  | 2023-08-17 | 01 - FUT in Progress | [6 empty] | 2023-08-23 |  | 2023-08-23 | [19 empty] | Pratik Mallick | Closed | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0007 | 3857 : Unloading and Receiving - Batch Updates | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263068 |  | Srujan K Aleti |  | Pratik Mallick | Arpita Roy |  |  | 2023-08-17 |  | 2023-08-17 | 00 - FUT Not Started | [6 empty] | 2023-08-21 |  | 2023-08-21 | [18 empty] | 3857 | Pratik Mallick |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0006 | 3845 : Update Inbound Truckboard - Critical Item Flag | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263116 |  | Jameel Hussain |  | Pratik Mallick | Mrudula NC |  |  | 2023-08-17 |  | 2023-08-17 | 00 - FUT Not Started | [6 empty] | 2023-08-28 |  | 2023-09-08 | [18 empty] | 3845 | Sankharupa Saha |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0009 | 2838 : Update Putaway - Direct Critical Item to Pickline | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263091 |  | Sandip Saha |  | Pratik Mallick | Sneha Ghosh |  |  | 2023-08-17 |  | 2023-08-17 | 00 - FUT Not Started | [6 empty] | 2023-08-31 |  | 2023-09-04 | [18 empty] | 2838 | Sankharupa Saha | In Progress | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0036 | 2856 : Cross Dock to Staging | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263299 |  | Sandip Saha |  | Pratik Mallick | Aratrika Banerjee |  |  | 2023-08-18 |  | 2023-08-18 | 00 - FUT Not Started | [6 empty] | 2023-09-14 | 2023-09-20 | 2023-09-20 | [17 empty] | 23/8 : Waiting for config changes. No WRICEF ID generated. | 2856 | Sankharupa Saha | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | PoC |  | NA | HU Packing during OBD to IBD creation | 21 - PoC Completed | EWM |  | E |  | Low |  |  |  | Sanjib Ghosh |  | Pratik Mallick |  |  | 2023-09-15 |  |  |  | 00 - FUT Not Started | [30 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0006 | 3765 : Inbound Door Proposal Update | 06 - Dev Completed | EWM |  | E |  | High |  | 263116 |  | Jagdish Babu |  | Pratik Mallick | Mayuri Sangvi |  |  | 2023-08-21 |  | 2023-08-21 | 00 - FUT Not Started | [6 empty] | 2023-09-04 |  | 2023-09-14 | [18 empty] | 3765 | Sankharupa Saha | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0007 | 705 : Deconsolidation Process_Unloading and Receiving | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263068 |  | Srujan K Aleti |  | Pratik Mallick | Pranali D Chavat |  |  | 2023-08-23 | 2023-08-23 | 2023-08-23 | 00 - FUT Not Started | [6 empty] | 2023-09-05 | 2023-09-08 | 2023-09-08 |  |  |  | 2023-09-01 | [14 empty] | 705 | Arpita Roy | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0010 | 705 : Deconsolidation Process_Putaway execution | 06 - Dev Completed | EWM |  | E |  | High |  | 263217 |  |  |  | Pratik Mallick | Pranali D Chavat |  |  | 2023-08-23 | 2023-08-23 | 2023-08-23 | 00 - FUT Not Started | [6 empty] | 2023-09-05 | 2023-09-18 | 2023-09-15 | [18 empty] | 705 | Arpita Roy |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0007 | 4847 : Wrong Product / New Found Item | 06 - Dev Completed | EWM |  | E |  | High |  | 263068 |  | Mansi Singh |  | Pratik Mallick | Arpita Roy |  |  | 2023-08-23 |  | 2023-08-23 | 00 - FUT Not Started | [6 empty] | 2023-09-05 |  | 2023-09-15 |  |  | 2023-08-24 | 2023-09-05 | [14 empty] | 4847 | Pratik Mallick | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0035 | 503 : Inbound Delivery from Matrics/Fusion Sites (New in ECC) | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263177 |  | Sanjib Ghosh |  | Pratik Mallick | Pratik Mallick |  |  |  | 2023-08-21 | 2023-08-21 | 00 - FUT Not Started | [6 empty] | 2023-09-08 |  | 2023-09-13 | [18 empty] | 503 | Jubaraj Swain | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0035 | 4789 : Pallet Type Traceability | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263177 |  | Sanjib Ghosh |  | Pratik Mallick | Pratik Mallick |  |  | 2023-08-21 |  | 2023-08-21 | 00 - FUT Not Started | [6 empty] | 2023-09-05 |  | 2023-09-14 | [18 empty] | 4789 | Jubaraj Swain | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD10315 | 3764 : Allow updates to delivery date after distribution to EWM (Order Life Cycle) | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263364 |  | Pratik Dixit |  | Pratik Mallick | Mayuri Sangvi |  |  | 2023-08-23 |  | 2023-08-28 | 00 - FUT Not Started | [6 empty] | 2023-09-05 | 2023-09-05 | 2023-09-07 | [18 empty] | 3764 | Aratrika Banerjee | In Progress | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0037 | 4788: Quarantine Release | 06 - Dev Completed | EWM |  | E |  | Medium |  | 263273 |  | Jagdish Babu |  | Pratik Mallick | Aratrika Banerjee |  |  | 2023-08-25 |  | 2023-09-14 | 00 - FUT Not Started | [6 empty] | 2023-09-22 |  | 2023-10-05 | [18 empty] | 4788 | Sankharupa Saha | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0021 | 2047 : Quality Hold | 06 - Dev Completed | EWM |  | E |  | High |  | 263338 |  | Nicholas |  | Pratik Mallick | Sneha Ghosh |  |  | 2023-08-24 |  | 2023-08-28 | 00 - FUT Not Started | [6 empty] | 2023-09-25 |  | 2023-09-26 | [18 empty] | 2047 | Pratik Mallick | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0010 | Putaway Screen - Add Stock Type Column | 06 - Dev Completed | EWM |  | E |  | Low |  | 263217 |  | Srujan |  | Pratik Mallick | Pranali D Chavat |  |  | 2023-08-25 |  | 2023-08-25 | 00 - FUT Not Started | [6 empty] | 2023-09-01 |  | 2023-09-01 | [18 empty] | 4928 | Arpita Roy | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0011 | 4922 : Add Protected Service Code to Outbound Truckboard TU Header | 06 - Dev Completed | EWM |  | E |  | Low |  | 262972 |  | Sandip Saha |  | Pratik Mallick | Mrudula NC |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 01 - FUT in Progress | [6 empty] | 2023-09-15 |  | 2023-09-15 | [18 empty] | 4922 | Mayuri Sanghvi | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0011 | 4703 : OB Truckboard: TC/ Temp Class Custom Fields | 06 - Dev Completed | EWM |  | E |  | Low |  | 262972 |  | Sandip Saha |  | Pratik Mallick | Mrudula NC |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 00 - FUT Not Started | [6 empty] | 2023-09-15 |  | 2023-09-15 | [18 empty] | 4703 | Mayuri Sanghvi | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0011 | 4900: Percentage HUs loaded and total HUs logic changes | 06 - Dev Completed | EWM |  | E |  | Low |  | 262972 |  | Sandip Saha |  | Pratik Mallick | Mrudula NC |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 00 - FUT Not Started | [6 empty] | 2023-09-15 | [20 empty] | 4900 | Mayuri Sanghvi | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0011 | 4953: Add Column for Case Pick, layer pick , FP pick relevance and percentage | 06 - Dev Completed | EWM |  | E |  | Low |  | 262972 |  | Sandip Saha |  | Pratik Mallick | Mrudula NC |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 00 - FUT Not Started | [6 empty] | 2023-09-15 | [20 empty] | 4953 | Mayuri Sanghvi | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | IDD0023 | EWM Plants to INSITE Pallet Mvmt | 05 - Dev On-Hold | EWM |  | I |  | Very High |  | 263465 |  | Pratik Dixit |  | Pratik Mallick | Raja Manish Singh |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 00 - FUT Not Started | [27 empty] | 4757 | Pratik Mallick | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0003 | 4616 : Product Master Days of Skip - New Fields | 06 - Dev Completed | EWM |  | E |  | Low |  | 263449 |  | Tharonie Kotha |  | Pratik Mallick | Sakshi Ahluwalia |  | 2023-09-15 | 2023-09-11 |  | 2023-09-11 | 00 - FUT Not Started | [6 empty] | 2023-09-11 | [20 empty] | 4616 | Sankharupa Saha | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | GLOBAL - NDC | 1056 : Monitor and Review Open Orders | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Srujan Kumar Aleti |  | Pratik Mallick | Sneha Ghosh |  |  | 2023-10-06 |  | 2023-10-10 | 00 - FUT Not Started | [6 empty] | 2023-10-20 | 2023-10-25 | [22 empty] | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0039 | 1166 : Case Picking Sorting: Warehouse order for task bundling, sizing & pickpath | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Sandip Saha |  | Pratik Mallick | Raja Manish Singh / Sneha Ghosh |  |  | 2023-09-18 |  | 2023-09-20 | 00 - FUT Not Started | [6 empty] | 2023-09-29 |  | 2023-10-06 | [18 empty] | 1166 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0013 | 5171 : Stock Removal Strategies - Mixing Center | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Sanjib Ghosh |  | Pratik Mallick | Sakshi Ahuliwalia |  | 2023-09-15 | 2023-09-18 |  | 2023-09-18 | 00 - FUT Not Started | [7 empty] | 2023-09-21 | 2023-10-05 | [18 empty] | 5171 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0038 | 5131 : Pickline Replenishment - Mixing Centre - RF Execution | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Jagdish Babu |  | Pratik Mallick | Pranali D Chavat |  | 2023-09-15 | 2023-09-15 | 2023-10-03 | 2023-10-03 | 00 - FUT Not Started | [6 empty] | 2023-10-13 | 2023-10-18 | [19 empty] | 5131 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0011 | Wave Management - Wave creation and initial release | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  |  | Pratik Dixit |  | Mayuri Sanghvi |  | 2023-09-15 | 2023-09-18 |  | 2023-09-18 | 00 - FUT Not Started | [6 empty] | 2023-10-03 |  | 2023-10-03 | [18 empty] | 4969 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0038 | 2142 : Pickline Replenishment - Mixing Center | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Jagdish Babu |  | Pratik Mallick | Pranali D Chavat |  | 2023-09-15 | 2023-09-19 |  |  | 00 - FUT Not Started | [6 empty] | 2023-10-06 |  | 2023-10-06 | [18 empty] | 2142 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0011 | 4968 : Automated Wave Re-Release after Replenishment | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Pratik Dixit |  | Pratik Mallick | Mayuri Sanghvi |  | 2023-09-15 | 2023-09-18 |  | 2023-09-18 | 00 - FUT Not Started | [6 empty] | 2023-10-03 |  | 2023-10-03 | [18 empty] | 4968 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0038 | 2160 : Replenishment Strategies - Mixing Center Unslotting | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Jagdish Babu |  | Pratik Mallick | Pranali D Chavat |  | 2023-09-15 | 2023-09-19 | 2023-09-22 | 2023-09-21 | 00 - FUT Not Started | [8 empty] | 2023-10-05 | [18 empty] | 2160 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0007 | 4950 : OS&D Gaps - New Found Item - Design/FS | 06 - Dev Completed | EWM |  | E |  | Very High |  |  |  | Mansi Singh |  | Pratik Mallick | Vamsi Balagonda |  | 2023-09-15 | 2023-09-14 |  | 2023-09-14 | 00 - FUT Not Started | [6 empty] | 2023-10-20 | [20 empty] | 4950 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0011 | 4927 : Staging - Future Hold Check | 06 - Dev Completed | EWM |  | E |  | Low |  |  |  | Nicholas |  | Pratik Mallick | Aratrika Banerjee |  | 2023-09-15 | 2023-09-20 | 2023-09-21 |  | 00 - FUT Not Started | [6 empty] | 2023-09-26 | [20 empty] | 4927 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0013 | 4411 : Replenishment Strategies - Customer BBD Enhancement | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Sanjib Ghosh |  | Pratik Mallick | Sakshi Ahuliwalia |  | 2023-09-15 | 2023-09-18 |  | 2023-09-18 | 00 - FUT Not Started | [6 empty] | 2023-09-22 |  | 2023-09-22 | [18 empty] | 4411 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0014 | 4744 : RF : Picking - Countback & counting down - WRICEF | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Sandip Saha |  | Pratik Mallick | Arpita Roy |  | 2023-09-15 | 2023-09-19 | 2023-09-20 | 2023-09-20 | 00 - FUT Not Started | [6 empty] | 2023-10-12 | 2023-10-14 | 2023-10-18 | [18 empty] | 4744 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0014 | 4745 : RF: Picking screen enhancements | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Sandip Saha |  | Pratik Mallick | Arpita Roy |  | 2023-09-15 | 2023-09-19 | 2023-09-20 |  | 00 - FUT Not Started | [6 empty] | 2023-10-06 |  | 2023-10-13 | [18 empty] | 4745 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 9 | EDD0013 | 4926 : Outbound Truckboard - Future Hold Check during PGI / Close TU | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Nicholas |  | Pratik Mallick | Mrudula NC |  | 2023-09-15 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 00 - FUT Not Started | [6 empty] | 2023-09-23 | 2023-09-28 | 2023-09-28 | [18 empty] | 4926 |  |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 8 | EDD0007 | 4701 : Ability for one product to have multiple pallet characteristics | 06 - Dev Completed | EWM |  | E |  | Low |  |  |  | Srujan |  | Pratik Mallick | Sankharupa Saha |  |  | 2023-09-13 |  | 2023-09-13 | 00 - FUT Not Started | [6 empty] | 2023-09-18 |  | 2023-09-26 | [18 empty] | 4701 | Pranali D Chavat |  | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0020 | 4705 - OB :load balancing by weight (delta) | 06 - Dev Completed | EWM |  | E |  | Very High |  |  |  | Sandip Saha |  | Pratik Mallick | Aratrika Banerjee |  |  | 2023-10-06 |  | 2023-10-09 | 00 - FUT Not Started | [6 empty] | 2023-10-31 | [20 empty] | 4705 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0009 | 5146 : Putaway Strategy - Prevent older stock to putaway to a bin with fresher date | 06 - Dev Completed | EWM |  | E |  | Low |  |  |  | Srujan |  | Pratik Mallick | Pranali D Chavat |  |  | 2023-10-05 |  | 2023-10-06 | 00 - FUT Not Started | [6 empty] | 2023-10-16 | 2023-10-19 | [19 empty] | 5146 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0011 | 4741 : OB Truckboard - EWM Potential Shorts (Pre-Cut) Report | 06 - Dev Completed | EWM |  | E |  | Very High |  |  |  | Srujan/Pratik Dixit |  | Pratik Mallick | Mayuri Sanghvi |  |  | 2023-10-10 |  | 2023-10-10 | 00 - FUT Not Started | [6 empty] | 2023-10-31 | [20 empty] | 4741 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0019 | 4952 : Capture actual loading position at time of loading | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Sanjib |  | Pratik Mallick | Kiran Gopi |  |  | 2023-10-05 |  | 2023-10-05 | 00 - FUT Not Started | [6 empty] | 2023-10-18 |  | 2023-10-18 | [18 empty] | 4952 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDDXXXX | 2931 : Monitor countback errors from the RF | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Sanjib Ghosh |  | Pratik | Sakshi |  | 2023-10-10 | 2023-10-10 |  | 2023-10-10 | 00 - FUT Not Started | [6 empty] | 2023-10-17 | 2023-10-18 | [19 empty] | 2931 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0019 | 5155 : Queue Management & Work Assignment | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Sandip Saha |  | Pratik Mallick | Pranali D Chavat |  | 2023-10-06 | 2023-10-06 |  | 2023-10-13 | 00 - FUT Not Started | [6 empty] | 2023-10-20 | [20 empty] | 5155 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDDXXXX | 2307 : Perform Counting RF Enhancements | 06 - Dev Completed | EWM |  | E |  | High |  |  |  | Mansi Singh | [8 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0010 | 5230 : Stock type of post-changed HU on putaway screen | 06 - Dev Completed | EWM |  | E |  | Low |  |  |  | Nicholas |  | Pratik Mallick | Pranali D Chavat |  |  | 2023-10-11 |  | 2023-10-11 | 00 - FUT Not Started | [6 empty] | 2023-10-16 |  | 2023-10-13 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0014 | 1203 : Manage Picking exceptions | 06 - Dev Completed | EWM |  | E |  | Very High |  |  |  | Danilo |  | Pratik Mallick | Vamsi Balagonda |  |  | 2023-10-19 | 2023-10-20 | 2023-10-20 | 00 - FUT Not Started | [27 empty] | 1205 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDDXXXX | 1295 : PGI for Parcel Orders | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Nicholas | [8 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDDXXXX | 1259 : Email to carrier when pickup is ready | 06 - Dev Completed | EWM |  | E |  | Medium |  |  |  | Pratik Dixit | [8 empty] | 00 - FUT Not Started | [27 empty] | 1259 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0009 | 5226 : Warehouse Structure - Mixing Center Template - Additional Storage Type for Mixing | 06 - Dev Completed | EWM |  | E |  | High | 2 - Medium | [11 empty] | 00 - FUT Not Started | [27 empty] | 5226 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 10 | EDD0010 | 5187 : Putaway Screen Enhancement | 06 - Dev Completed | EWM |  | E |  | High | 2 - Medium | [11 empty] | 00 - FUT Not Started | [27 empty] | 5187 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0030 | 5243 : Product Master - Upload Program for Custom Fields | 06 - Dev Completed | EWM |  | E |  | High | 2 - Medium | [11 empty] | 00 - FUT Not Started | [27 empty] | 5243 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD00001 & EDD00002 | 5647 : Monitor and Review Open Orders - Four New Fields | 06 - Dev Completed | EWM |  | E |  | High | 2 - Medium | [11 empty] | 00 - FUT Not Started | [27 empty] | 5647 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0038 | 4983 : Pickline Replenishment - Layer Picking (Mixing Center) | 06 - Dev Completed | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [27 empty] | 4983 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0052 | 5142 : Stock Removal Strategies - Mixing Center - Days of Skip Upload Program | 06 - Dev Completed | EWM |  | E |  | High | [12 empty] | 00 - FUT Not Started | [27 empty] | 5142 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | IDD | 1662 : Interface 1: EWM to Kaleris - Create/Update TU - Design | 06 - Dev Completed | EWM |  | I |  | Very High | [12 empty] | 00 - FUT Not Started | [27 empty] | 1662 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0014 | 5492 - Monitor countback errors from the RF - RF Changes for Exception Handling | 06 - Dev Completed | EWM |  | E |  | High | [12 empty] | 00 - FUT Not Started | [27 empty] | 5492 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0014 & EDD0019 | 5154 : RF: Picking screen enhancements - Specify Number of Pallets Used | 06 - Dev Completed | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [27 empty] | 5154 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD | 5532 : ZISH Output for Creation of Inbound Shipment - Modify | 06 - Dev Completed | EWM |  | E |  | Very High | [12 empty] | 00 - FUT Not Started | [27 empty] | 5532 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD | 4791 : Receipt from EWM site | 06 - Dev Completed | EWM |  | E |  | Low | [12 empty] | 00 - FUT Not Started | [27 empty] | 4791 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0014 | 5327 : Monitor countback errors from the RF - PI Document Exception Scenarios | 06 - Dev Completed | EWM |  | E |  | High | [12 empty] | 00 - FUT Not Started | [27 empty] | 5327 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 11 | EDD0011 | 5160 : OB Door Selector - TU Door Assignment | 06 - Dev Completed | EWM |  | E |  | High | [12 empty] | 00 - FUT Not Started | [27 empty] | 5160 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0053 | 5012 : Automation for determining pickline slotting (Layer) | 06 - Dev Completed | EWM |  | E |  | High | 3 - Low |  |  | Sandip Saha |  |  | Jubaraj Swain |  | 2024-01-12 |  |  |  | 00 - FUT Not Started | [6 empty] | 2023-12-21 | 2024-01-12 | 2024-01-12 | [18 empty] | 5012 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0054 | 927 : Order Cancellation Automation | 06 - Dev Completed | EWM |  | E |  | High | 3 - Low |  |  | Aalla |  |  | Sakshi Ahluwalia |  |  | 2023-12-18 | 2023-12-18 |  | 00 - FUT Not Started | [6 empty] | 2024-01-17 | [20 empty] | 927 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0006 | 4920 : Critical Items Flag on TU Header & Item Level Flagged on IB TU - Add Outbounds & QT Time | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 02 - FUT Complete | [6 empty] | 2023-12-15 | [20 empty] | 4920 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0006 & EDD0011 | 5676 : IB and OB Truckboard - Add Trailer Moves Button | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Varsha Singhal | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-01-03 | [20 empty] | 5676 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0006 | 5799 : IB Truckboard - Fix Logic in IB Door Proposal | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-12-15 | [20 empty] | 5799 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0011 & EDD0006 | 5951 : IB and OB Truckboard - Add Trailer Moves Button - Same Source/Dest. Door | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Varsha Singhal | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-01-03 | [20 empty] | 5951 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0045 | 2307 : Perform Counting - RF Enhancements | 06 - Dev Completed | EWM |  | E |  | Very High | [6 empty] | Pranali Dnyaneshwar Chavat |  |  | 2023-11-14 | 2023-11-14 |  | 00 - FUT Not Started | [6 empty] | 2024-01-01 | 2024-01-22 | 2024-01-22 | [18 empty] | 2307 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0046 | 2379 : Post Differences - Difference Analyzer | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-11-14 |  | 2023-11-14 | [18 empty] | 2379 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | IDD010561 - ECC | 4790 : Receipt from Vendor ASN (IDD010561) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-11-20 | [20 empty] | 4790 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD | 4743 : OB: Picking - Suspend/Park/Resume - RF | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Raja Manish Singh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-01-03 | [20 empty] | 4743 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0011 | 5630 : OB: Picking - Suspend/Park/Resume - Truckboard | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-11-16 | [20 empty] | 5630 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | IDD0023 | 5678 - INSITE - Redesign Build - FS Approval and NEW Program Structure Build | 06 - Dev Completed | EWM |  | I |  | Very High | [6 empty] | Vamsi Balagonda |  |  | 2023-12-12 | 2023-12-12 |  | 00 - FUT Not Started | [6 empty] | 2024-02-29 |  |  |  |  | 2024-01-01 | [15 empty] | 5678 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD | 5189 : Manual Move Enhancement - RF Navigation Changes | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh |  |  | 2023-12-19 | 2023-12-19 |  | 00 - FUT Not Started | [6 empty] | 2023-12-29 | 2024-01-22 | 2024-01-22 | [18 empty] | 5189 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD0006 | 5237 - Amazon Flex Cage Transfer | 06 - Dev Completed | EWM |  | E |  | Low | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-12-13 | [20 empty] | 5237 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 12 | EDD | 5239 : Manual Move Availability Check | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2023-12-12 | [20 empty] | 5239 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | FDD0017 | 5445 : Email to Carrier | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh |  |  | 2024-01-08 | 2024-01-08 |  | 00 - FUT Not Started | [6 empty] | 2024-02-26 | [20 empty] | 5445 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD0011 | 5845 - Wave Creation for Case/Full Pallet- Slotting program enhancement | 06 - Dev Completed | EWM |  | E |  | Very High | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [27 empty] | 5845 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD0021 | 5294 : Quality hold product replen automation | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Sakshi Ahluwalia | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-22 | [20 empty] | 5294 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD | 5235 : QT Release Calc - Blind Recept | 13 - Deferred | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [27 empty] | 5235 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD0054 | 5582 : Mfg/Exp Age Method Identifier | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Varsha Singhal |  |  | 2024-01-08 | 2024-01-08 |  | 00 - FUT Not Started | [6 empty] | 2024-02-20 | [20 empty] | 5582 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | FDD0018 | 5816 : Pork Pen Compliant Text Mapping | 06 - Dev Completed | EWM |  | F |  | High | [6 empty] | Mayuri Sangvi |  |  | 2024-01-12 | 2024-01-12 |  | 00 - FUT Not Started | [6 empty] | 2024-03-04 | [20 empty] | 5816 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD0048 | 5846 : Interface 2: Kaleris to EWM: Create/Update TU - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Mayuri |  |  | 2024-04-04 | 2024-04-05 |  | 00 - FUT Not Started | [6 empty] | 2024-05-02 | [20 empty] | 5846 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD0049 | 5847 : Interface 3: Yard Warehouse Task Create – Outbound from EWM - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Kavya Vippala |  |  | 2024-04-04 | 2024-04-05 |  | 00 - FUT Not Started | [6 empty] | 2024-04-19 | [20 empty] | 5847 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD0050 | 5867 : Interface 4: Yard Warehouse Task Create - Inbound from YMS - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Kiran Gopi Kotipalli |  |  | 2024-04-04 | 2024-04-05 |  | 00 - FUT Not Started | [6 empty] | 2024-05-03 | [20 empty] | 5867 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD0051 | 5872 : Interface 5: Yard Warehouse Task Confirm - Inbound from YMS - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Kiran Gopi Kotipalli |  |  | 2024-04-04 | 2024-04-05 |  | 00 - FUT Not Started | [6 empty] | 2024-05-03 | [20 empty] | 5872 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | FDD0017 | 5328: Temp Override | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-26 | [20 empty] | 5328 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Production - SWAT | Sprint 13 | EDD0004 | ZISH issue when multiple OBD available in OB shipment - Single Stop | 06 - Dev Completed | EWM |  | E |  | Low |  |  |  | Sanjib Ghosh |  |  | Pratik Mallick |  |  | 2024-01-17 | 2024-01-18 |  | 00 - FUT Not Started | [8 empty] | 2024-01-19 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Inbound - Crossdock Inactive | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Pratik Mallick | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-02-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Quality Hold - Error in monitor | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-19 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Inbound - Wrong product dump in RF | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kavya Vippala | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-20 |  | 2024-02-20 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | Crossfunctional | Crossfunctional - Enhancement table entry missing | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-12 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Inbound /Truckboard - Flip IB to OB | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Varsha Singhal | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-15 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD00038 | Outbound/Truckboard - Replensihment | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pranali Dnyaneshwar Chavat | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Physical Inventory - RF issues | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Pranali Dnyaneshwar Chavat | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-16 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Truckboard - TU Disappear | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-02-14 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Truckboard - No Log came in Wave release | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Truckboard - WO PSHu Mapping | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Shortage Report - Layer Pick - Wave Not Showing in Report | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-16 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Cartonisation - wrong HU bundling | 27 - Resolved | EWM |  | E |  | Very High | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-19 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Outbound /Picking - picking strategy enhancement | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sakshi Ahluwalia | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Replenishment - System not checking existing replenishment tasks | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD0011 | 5938 - OB Truckboard - Update Yard Management Functionality | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-04-10 | [20 empty] | 5938 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD0006 | 5582 - EDD0006 - Mfg/Exp Age Method Identifier | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Varsha Singhal |  |  | 2024-01-08 | 2024-01-08 |  | 00 - FUT Not Started | [6 empty] | 2024-02-28 | [20 empty] | 5582 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | RF Bin to Bin - Update Control Table Value for B2B | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71314: Addition of checkbox to handle empty HU scenario | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sakshi Ahluwalia/Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-23 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Product Idoc fail in WWQ - Material UoM =DS/MO issue | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Pranali Dnyaneshwar Chavat | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-20 |  | 2024-02-20 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Shortage Report - Removable Stock | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | OB Truckboard - Additional check for Load balancing | 01- FSD not received | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Control Table Update for EFWR | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kavya Vippala | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-20 |  | 2024-02-20 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD0011 | 5969 - Shortage Report -Delivery Cut Change for Park Suspend /Resume | 06 - Dev Completed | EWM |  | E |  | Low | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-02-23 | [20 empty] | 5969 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Control Table update for EFWD | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kavya Vippala | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-03-01 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Truckboard - Cap wave during wave release | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Order Cancellation - Order Cancellation Issue | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sakshi Ahluwalia | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Scheduling Report - Layer Qty field Calc. Change the SRCI condition. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71315 - OB Truckboard - Total number of HU coming wrong | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | OB Truckboard - Issue in OB Truckboard WOCR creation - Park suspend resume | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Outbound/Loading - Issue in Loading screen while modifying load position | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71318: outbound truckboard - 2 Items | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD0011 | Re-Release program not filtering wave based on wave release date and time | 27 - Resolved | EWM |  | E |  | Low | [12 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | outbound truckboard - Critical Item flag not worked in WWQ | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | outbound truckboard - Shortage report Adjust quantity | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | outbound truckboard - OB Truckboard Wave release header status remains Red even after both Waves successful | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | Wave Re-Release Program - Wave Re-Release Program Needs to have multiple selection for release status | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | outbound truckboard - Door distance calculation not working OB Truckboard | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Slotting Program - 2 Bugs identified | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Load Balancing - Error message "load cannot be saved due to HU in row 10 position B" when there was nothing in that position. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71319: Posting Change authorization - Add "RG" stock type into the list of stock types such as Q1, Q2, etc. that require quality control team access to remove | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Cartonization Planning - "Cap wave was failing on every large TU. SLG1 would show error during PSHU creation for almost every TU. Take any large TU from WWQ and run cap wave transaction and see the log" | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Countback WOs for PI showing in "D" status - WOs for PI specifically countback PI documents are still showing in process after PI doc successfully posted | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pranali D Chavat | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | PoC | Sprint 14 | EDD | Batch Specific HU Neutral Picklines - Andres to change config for LP02 in WWD to prototype | 04 - Dev in progress | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [27 empty] | 6048 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | Product Master - 6 New products failed to replicate to EWM due to UOM issue | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pranali D Chavat | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | EDD | BOL - Third party charges bill to, pallet information, text Y032 in special instruction is not printing. | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71320: Outbound Park Suspend Resume - REPL created 2 WOs for the same stock/bin after applying missing exception code | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71322: OB Truckboard - Wave release log need the product details and wave item | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71323:Picking Strategy - Case pick wave pick going to Layer pickline | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Jubaraj Swain | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Dry Run Bug | Sprint 13 | FDD | Packing Manifest - Delivery date issue on packing manifest form | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 13 | EDD | D#71325:Quality Holds - When creating hold IDs in one warehouse, the same hold IDs are showing in all warehouse. | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha Ghosh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71307: OB Truckboard - For Group picking close TU should not so Cross Delivery HU twice for multiple deliveries, use the delete duplicate for cross delivery also. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71389: OB Truckboard - Shortage Report not displaying Replen WO | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Mayuri Sanghvi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71329 - RF Case Picking | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja Manish Singh | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 13 | EDD | D#71316 - Pick percentages are not coming up correctly on Truckboard | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71496 - QT Date and time not updaed in PRDI | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71532 - "Error - Inbound delivery not created"- for OSD New item | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71533 - 2024-EWM NA Fort Worth MC_ITC2 ¦ Data display issue while executing Inbound Scheduling Report using BOL filter | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71412 - 2024-EWM NA Fort Worth MC ¦ Inbound_Vendor Overage_Error while creating New HU which is not present in IBD | 27 - Resolved | EWM |  | E |  | Very High | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD0053 | 6006 - Show Layer Demand and Bins Needed Log - Slotting Program Enhancement | 06 - Dev Completed | EWM |  | E |  | Very High | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-04-19 | [20 empty] | 6006 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD0010 | 5832 - Columbia City Defects | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pranali | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-04-04 | [20 empty] | 5832 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD010778 | 6067 - INSITE - Integration testing of redesign with Insite Team | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [27 empty] | 6067 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD0014 | 6048 - Layer & Case Pick Selection Logic | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-04-11 | [20 empty] | 6048 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 13 | EDD | 5938 - OB Truckboard - Update Yard Management Functionality | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Varsha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-03-07 | [20 empty] | 5938 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71677 - Door Not Populated automatically in Yard Management | 27 - Resolved | EWM | EWM-NA-Phase1-Sprint3 | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71538 - Outbound - Unable to perform yard movement for TU in Outbound truckboard | 27 - Resolved | EWM | EWM-NA-Phase1-Sprint3 | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71685 - Dump error in ECC for ME21N | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71713 - Dump Error for Slotting Program | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71632 - Q-HOLD HU stock type not changed. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71599 - Stock type QT not changed to AV | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71608 - system allowed to load Quality Hold HU's to Door | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71570 - Outbound DN Pallet Line inserted into STO. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71388 - Extra enter on pick denial (zero or short pick) | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pranali | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | IDD0047 | 4805 - Interface 1: EWM to Kaleris: Create/Update TU | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Kavya Vippala |  |  | 2024-04-04 | 2024-04-05 |  | 00 - FUT Not Started | [6 empty] | 2024-04-19 | 2024-04-26 |  |  |  |  | 2024-04-19 | [14 empty] | 4805 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71323 Case Pick wave going to pick from Layer Pickline | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71819: Outbound - PSHU Number is not present for the products | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71780: EWM_NA_Outbound_Prebilt is logging off automaically while performing picking. | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71859 - 2024-EWM NA Fort Worth MC_ITC1 ¦ Inbound_Codedate indicator is disappering once we create the HUs for the line item | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71857 - QH01 WT unable to confirm in RFUI | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71794 - EWM_NA_Outbound_Posting change WT is not created after confirming the replenishment task for the picking exception 'Missing' and 'Damage'. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71793 - Outbound - Unable to create Inbound delivery for STO after PGI is sent from Matrics as SPED output type is failing with error | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71746 - Outbound - 2 waves got created for a TU having multiple deliveries | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71827 - Add message to indicate PSHU creation in wave release and re-release program | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#71824 - SPED Enhancement should not fail in case of erroneous record in shipment pallet table | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71823 - Picking Strategy based on SRCI - Case Pick Wave task going to Layer Pickline | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71528 - Wave Release and Re-Release Program PSHU mapping issue | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71957 - Change Batch not working in RF | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#71916 - Line Retrieval task not created | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71931 - FUT Defect - Case Picking - Missing and Damage need to remove HU input in logic | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#71978 - OB truckboard Selection screen not filtering some TUs in WWQ-300. Need to check the logic of stanadard and implement the same in OB trucboard | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72016 - Replanishment Calculation correction for Order based Repl requirement quantity - addition logic added to mitigate the standard issue. | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72072 - Date is in past error message to be removed in PI counting | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72001 - 551 M.type Partial qty not updated correctly in INSITE | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 15 | EDD | D#72015 - getting error " can not post goods issue for the delivery item 00000" for Shortage | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72019 - 919, 909 & 921 m.type not updated coreectly in Insite | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72023 - IBD not Distributed to 0490 due to missing values | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72024 - 641 m.type failed in Insite | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72078 - storage sec. indicator not updated correctly using slotting program | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 14 | EDD0003 | 6020 - Master Data ECC to EWM - Integration - CLFMAS Change Pointers | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-04-24 | [20 empty] | 6020 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0035 | 6198 - Program to update HU Status in ECC for IB STOs involving Matrics sites | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-02 | [20 empty] | 6198 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0008 | 6030 - Return Enhancement - RA Visibility | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-10 | [20 empty] | 6030 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0086 | 6203 - Report for SLOC Update for Cutover | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Veereshravi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-03 | [20 empty] | 6203 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 15 | IDD0070 | 6426 - Messaging - Cancellation Request from EWM to WCS - CAN001 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Rohit | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-06-04 |  | 2024-06-04 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72138 - 999 m.type not processed correctly in Insite | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect |  | IDD | D#72205 - X31,947 M.type Qty not updated correctly | 27 - Resolved | EWM |  | I |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | IDD | D#72205 - X31,947 M.type Qty not updated correctly | 27 - Resolved | EWM |  | I |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | IDD | D#72215 - Acknowledgement not received from Insite | 27 - Resolved | EWM |  | I |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | IDD | D#72237 - 323 m.type rejected in Insite | 27 - Resolved | EWM |  | I |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | IDD | D#72256 - 552 Movement type - Quantity is not updated correctly in InSite - Partial quantity 100 CSE | 27 - Resolved | EWM |  | I |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72163 - KT_ Yard management change for IB/OB Truck board based on Training input | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72195 - Instead of adding SHORT system is adding OVER | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72196 - User not able to back out of New Hu screen in Receiving by TU | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72212 - KT_DECON new HU is not being recognised | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72257 - Pick and Load - Loading task creation WO related Error | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 14 | EDD | D#72267 - Rough bin det and Picking strategy bug | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0045 | 6021 - Inventory Cycle Counting Enhancements | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-21 | [20 empty] | 6021 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0011 | 6050 - Shortage Report Error Visibility - Gridlock | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-17 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 15 | IDD0071 | 6424 - Messaging - WT Cancellation Response from WCS to EWM - CAN002 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Low | [6 empty] | Rohit | [5 empty] | 00 - FUT Not Started | [9 empty] | 2024-06-04 |  | 2024-06-04 | 2024-06-04 |  | 2024-06-04 | [14 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 15 | IDD0072 | 6425 - Messaging - Cancellation Request from WCS to EWM - CAN003 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Low | [6 empty] | Rohit | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-06-05 |  | 2024-06-05 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 15 | IDD0068 | 6420 - Messaging - Internal Mvmnt/Adhoc Pallet Request - INT001 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Kavya |  |  |  | 2024-05-10 | 2024-05-10 | 00 - FUT Not Started | [6 empty] | 2024-05-24 |  | 2024-05-24 | 2024-05-24 |  | 2024-05-24 | 2024-05-31 |  | 2024-06-07 | [14 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 15 | IDD0067 | 6418 - Messaging - Internal Mvmnt/Adjs Inv Status Update - INT002 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Veereshravi |  |  |  | 2024-05-16 | 2024-05-16 | 00 - FUT Not Started | [6 empty] | 2024-05-29 |  | 2024-06-06 | 2024-05-20 |  | 2024-05-27 | 2024-05-29 |  | 2024-06-06 | [14 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | IDD0047 | 4805 - Interface 1: EWM to Kaleris: Create/Update TU | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [27 empty] | 4805 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | IDD0048 | 5846 : Interface 2: Kaleris to EWM: Create/Update TU - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [27 empty] | 5846 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | IDD0049 | 5847 : Interface 3: Yard Warehouse Task Create – Outbound from EWM - Build | 06 - Dev Completed | EWM |  | I |  | High | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [27 empty] | 5847 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | IDD0050 | 5867 : Interface 4: Yard Warehouse Task Create - Inbound from YMS - Build | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Kiran | [5 empty] | 00 - FUT Not Started | [27 empty] | 5867 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | IDD0051 | 5872 : Interface 5: Yard Warehouse Task Confirm - Inbound from YMS - Build | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Kiran | [5 empty] | 00 - FUT Not Started | [27 empty] | 5872 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72278 - KT DEFECT - Fixing the PSHU Sequence number so it will sort numerically. Changing the Data Element ZEWM_E_PSHUSEQ from CHAR10 to NUMC3 for custom field ZZSORTSEQ. | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72320 - Fort Worth KT Bug: Countback Issues | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Kiran | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72331 - KT_Fortworth KT Issue in Load Balancing | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72341 - KT: Shortage report - should not show 0 qty on shortage - partial showing on release | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | FDD | D#72344 - KT: BOL and Packing List shipment totals are not matching BOL/pack list | 06 - Dev Completed | EWM |  | F |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72370 - PSHU creation Issue | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72379 - OB Truckboard Slowness - Close Yard Managemnt , Close TU Priority , Close Assign Door | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72412 - KT-Door not auto populating on IB receiving | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72450 - LTL config and dev addition for Wave release | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 15 | EDD | D#72239 - 343 M.type Mixed pallet failed in Insite | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | ITC Defect | Sprint 14 | EDD | D#72273 - 555 & 553 M.type failed in Iniste | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0011 | 6031 - Truck Board- Need visibility to out of service trailers when assigning TU | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-10 | [20 empty] | 6031 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD | 6032 - Kaleris Integration - Alternate SCAC | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Kavya | [5 empty] | 00 - FUT Not Started | [27 empty] | 6032 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0038 | 6363 - Replen Requested Qty Hide | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-14 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0014 | 6364 - Case/Layer Breakout Qty - RF | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-17 | [20 empty] | 6364 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD0006/EDD0011/EDD0012 | 5295 - Common yard movements | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-28 | [20 empty] | 5295 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 15 | EDD00683 | 6339 - ECC - YMHL Customer ASN | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-05-14 | [20 empty] | 6339 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72529 - Wave release stopped, as no PSHU found | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72530 - PSHU not found for the wave when I released the wave | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72513 - I completed the pick tasks and dropped the pallet at the shrink wrap. The shrink wrap task was not confirmed (not yet taken to staging) and the order wasn't allowed to cancel. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72588 - Outbound Truckboard Error | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72578 - KT- Not able to create LTL Empty Trailer from ZEWM_CICO Tcode | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72570 - Putaway to pickline for CP02 and CPC1_EFWD | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Kiran | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72587 - Execution of zerofill failed but warehouse putaway tasks still created. | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | FDD | D#72577 - LTL BOL/Packing Manifest Issue | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Regression Defect | Sprint 15 | EDD | D#72543 - Regression_STO from 4842 to 0220_Unable to perform the PGR for inbound delivery in 0220 plant. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72343 - KT: Load balancing - rebalancing after loading has started, stacked HUs | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72535 - WTList Not allowing to proceed | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72514 - Message queue not clearing out once shipment deleted in ECC. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72609 - Wave release not succesfully created, CS01, WOCR | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 15 | EDD | D#72688 - QT removal upon Receipt | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72660 - Wave can not be released | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72800 - Auto shuttle IBD(0478) created with batch 1 | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Regression Defect | Sprint 15 | EDD | D#72760 - Insite Received data as WM000COL instead of EWM | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72734 - Picking and loading statuis are not reflecting the correct stop ligth and loading % is shwoing 200 | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72626 - Access for custom transaction YEWM_SLOC_UPD for production cutover execution | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Veereshravi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72698 - Park Suspend and Resume - for Delivery Cut | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72676 - Release Wave is not done however release log says is completed | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72378 - KT: task should not go beyond full pallet quantity form pick line | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72843 - QT date and time not update in inbound delivery | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72785 - Load Plan indicated Mixed HU was 114in tall. Allowed load plan with height restriction. HU Height actually 37in. | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72848 - PSHU matching additional changes | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | CR | Sprint 15 | EDD | D#72847 - if wave released previously, prepopulate the staging area during next release and gray out | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Regression Defect | Sprint 15 | EDD | D#72859 - 644 M.type Data Records not passed to Insite | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Vamsi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72805 - UAT Data_Inbound STO_HUs are not reflecting in IBD | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Regression Defect | Sprint 15 | EDD | D#72714 - PGR not updated in ECC | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 15 | EDD | D#72668 - PI Issues | 27 - Resolved | EWM |  | E |  | High | [6 empty] | Ram | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72870 - It would let me confirm the new item, but when I go to putaway it send me the error message " error posting goods receipt" | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Veereshravi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72734 - Picking and loading statuis are not reflecting the correct stop ligth and loading % is shwoing 200 | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72831 - Load Balancing to heavy in nose. pallets can be moved from rows 3 and 4 towards the back and that would help balance the load. the logic to where to put the pallets should be looked at. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#73027 - Case picking not recognizing Layer and Case count entry. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#73127 - Can not recieve pallets from this shipment using F4 - New Hu | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Kiran | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72988 - Inbounded a Full pallet and the system sent me to pick the pallet instead of putting away in a reserve location | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72952 - Posting Change Overage Node not sorting properly | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#72956 - CG Date Calculation not working as expected. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 15 | EDD | D#73117 - Mixed pallet deconsolidation will not accept new ticket when trying to put away it puts the ticket number in the product space in EWM | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 15 | EDD | D#73061 - FUT_Quality Hold Issues | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha/Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | WRICEF | Sprint 16 | EDD0011, EDD0006, EDD0012 | Common yard movements | 06 - Dev Completed | EWM |  | E |  | High | [6 empty] | Mayuri Sangvi | [5 empty] | 00 - FUT Not Started | [27 empty] | 5295 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 16 | IDD0056 | 6423 - Messaging - Inbound Pallet Induction - INB001 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Gourav |  |  |  | 2024-10-06 | 2024-10-06 | 00 - FUT Not Started | [6 empty] | 2024-06-17 |  | 2024-06-17 | 2024-06-10 |  | 2024-06-10 | 2024-06-17 | [14 empty] | 6423 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 16 | IDD0057 | 6421 - Messaging - Inbound Pallet Location Confirmation (Reject Lane) - INB002 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Low | [6 empty] | Rohit |  |  |  | 2024-05-16 | 2024-05-16 | 00 - FUT Not Started | [6 empty] | 2024-05-27 |  | 2024-06-10 | 2024-05-17 |  | 2024-05-17 | 2024-05-27 |  | 2024-06-10 |  | 06 - Dev Completed | [10 empty] | 6421 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 16 | IDD0058 | 6422 - Messaging - Inbound Pallet Location Update/Confirmation - INB003 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Gaurav |  |  |  | 2024-06-12 | 2024-06-12 | 00 - FUT Not Started | [6 empty] | 2024-06-24 |  | 2024-06-24 | 2024-06-18 |  | 2024-06-18 | 2024-06-24 | [14 empty] | 6422 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 16 | IDD0066 | 6417 - Messaging - Internal Mvmnt/Inventory Control Notification - INT003 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Medium | [6 empty] | Vamsi |  |  |  | 2024-06-12 | 2024-06-12 | 00 - FUT Not Started | [6 empty] | 2024-06-20 |  | 2024-06-20 | 2024-06-14 |  | 2024-06-14 | 2024-06-20 |  | 2024-06-20 | [12 empty] | 6417 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 16 | IDD0069 | 6419 - Messaging - Internal Mvmnt/Adhoc Pallet Request Confirmation - INT004 - (EWM <-> Integration Suite (IS)) | 06 - Dev Completed | EWM |  | I |  | Low | [6 empty] | Rohit |  |  |  | 2024-06-10 | 2024-06-10 | 00 - FUT Not Started | [6 empty] | 2024-06-20 |  | 2024-06-20 | 2024-06-11 |  | 2024-06-11 | 2024-06-20 |  | 2024-06-20 | [12 empty] | 6419 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 17 | IDD0055 | 6415 - Item Master Download_MAT001 | 06 - Dev Completed | EWM |  | I |  | Medium |  | 267552 |  |  |  |  | Kiran | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-22 | [20 empty] | 6415 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | EDD | D#73398 - Order Cancellation program not working for picking not started and planned TUs | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | EDD | D#73387 - Cannot Release QT manually and Update User Status has context menu | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | EDD | D#73407 - Put same product, multiple batches on hold (same hold ID) | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | EDD | D#73370 - Columbia City Staging/Outbound screen freezing when ticket is scanned | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | EDD | D#73441 - QM Handling Units tcode running slowly | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | Cutover/Hypercare Defect | Sprint 16 | FDD | D#73437 - E-mail to carrier confing is not correctly updated in WWP , hence created a confing RT :0000268125 to move to WWP | 27 - Resolved | EWM |  | F |  | Low | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 16 | EDD | D#73424 - QHold validation not checking for the HU-(with more than one product) in the loading screen. | 27 - Resolved | EWM |  | E |  | Low | [6 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 16 | EDD | D#73409 - LTL Close TU and Check Out is not working! | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 16 | EDD | D#73403 - Add HU Status Change Code back to "ZSPE" output types processing routine. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Pratik M | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 16 | EDD | D#73369 - ECC Tech Cutover - Need to Transport subsequent TRs with missing objects for failed TRs for OB truckboard. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 16 | EDD | D#73307 - QT stock not auto updating to AV | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 16 | EDD | D#73304 - Assigned Trailer to TU in YRD management screen but move is not in Kaleris | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | UAT Defect | Sprint 16 | EDD | D#73271 - New HU batch split error | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja/Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 16 | EDD | Defect#73502 - Common yard - Inbound Truckboard - Yard Managemnt - Docking - system creating warehouse task to another warehouse. | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 3 | FUT Defect | Sprint 16 | EDD | D#73061 - FUT_Quality Hold Issues while Close TU | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0014 | D#73764 - Countback screen lockup | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 264307 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [12 empty] | 2024-07-08 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDXXXX | D# 73772 - Monitor not working because of memory issue | 27 - Resolved | EWM |  | E |  | High | 1 - High | [5 empty] | Shane Cotter | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 | [5 empty] | 2024-07-08 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | ED0021 | D# 73775 - Quality Hold Defect - Item & Code Date Range Entered, inserting QH on every item in that code date range | 27 - Resolved | EWM |  | E |  | High | 1 - High | 268453 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 |  | 2024-07-08 |  |  |  | 2024-07-08 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0048 | D#73761 - Kaleris Integration - Inbound Empty Trailer Checkin Creating Multiple TU's in EWM | 06 - Dev Completed | EWM |  | E |  | High | 1 - High | 268437 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 |  | 2024-07-08 |  |  |  | 2024-07-08 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73765 - Outbound truckboard header not calculating partial cases correctly | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268475 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-10 | [5 empty] | 2024-07-09 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0009 | D#73742 - Putaway is ignoring height limitation on locations and over directing HU's to bins | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268441 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-09 |  | 2024-07-09 |  |  |  | 2024-07-08 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0010 | D#73735 - Mixed Pallet Putaway - Putback to stock after picking | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268446 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 |  | 2024-07-08 |  |  |  | 2024-07-06 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0027 | D#73784 - Appointment time is not updated in EWM | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | [5 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-09 |  | 2024-07-09 |  |  |  | 2024-07-08 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0039 | D#73759 - Sequence issue in mixed pallet PSHU | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268445, 268465 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 | 2024-07-10 |  |  |  |  | 2024-07-08 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73738 - Sort Wave release by appointment date and time | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268438 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-10 | [5 empty] | 2024-07-09 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0014 | D#73752 - Need custom tcode to maintain countback table in EWM | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268444 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 |  | 2024-07-08 |  |  |  | 2024-07-09 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD010778 | D#73779 - Insite - Exclude returns not have HU on feed to Insite | 06 - Dev Completed | EWM |  | E |  | Low | 3 - Low | 268472 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-11 | [5 empty] | 2024-07-09 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDDXXXX | D#73776 - Need capacity calculation form /SCWM/ADHU to work (technical issue) | 06 - Dev Completed | EWM |  | E |  | Low | 3 - Low | [5 empty] | Raja | [5 empty] | 00 - FUT Not Started | [12 empty] | 2024-07-09 | [16 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0012 | D# 73744 - Missing Asterik | 06 - Dev Completed | EWM |  | E |  | Low | 3 - Low | 268434 |  |  |  |  | Kiran | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-08 |  | 2024-07-08 |  |  |  | 2024-07-08 |  |  |  | 06 - Dev Completed | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | FDD0017 | D#73737 - BOL auto-email setup | 06 - Dev Completed | EWM |  | E |  | Low | 3 - Low | 268450 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-10 |  | 2024-07-10 |  |  |  | 2024-07-09 |  |  |  | 04 - Dev in progress | [12 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 17 | IDD0059 | 6412 - Host Order Download_OUT001 | 06 - Dev Completed | EWM |  | I |  | Low |  | 267553 |  |  |  |  | Rohit | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-26 | [20 empty] | 6412 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 17 | IDD0060 | 6413 - Outbound Host Order Confirmation | 06 - Dev Completed | EWM |  | I |  | Medium |  | 268514 |  |  |  |  | Veeresh | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-26 | [20 empty] | 6413 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0061 | 6411 - Outbound Inventory Adjustment | 06 - Dev Completed | EWM |  | I |  | Medium |  | 269681 |  |  |  |  | Neha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-16 | [20 empty] | 6411 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 17 | IDD0063 | 6410 - Outbound Pallet Pre-Stage Request OUT006 | 06 - Dev Completed | EWM |  | I |  | Medium |  | 268759 |  |  |  |  | Gourav | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-28 | [20 empty] | 6410 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 17 | IDD0064 | 6409 - Outbound Pre-Stage Confirmation OUT007 | 06 - Dev Completed | EWM |  | I |  | Medium |  | 268587 |  |  |  |  | Ramya | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-29 | [20 empty] | 6409 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0019 | D#73807 - Door Docking on OB finding completed door | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268474 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-09 |  | 2024-07-09 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0020 | D#73810 - Load Balancing | 06 - Dev Completed | EWM |  | E |  | High | 1 - High | 268482 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-07-10 |  | 2024-07-10 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Cutover/Hypercare Defect | Sprint 17 | EDD0038 | D#73812 - Replen sending HU to a bin that already has 1 HU when strategy is next empty bin | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268583 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0053 | D#73811 - Slotting Program Issue | 06 - Dev Completed | EWM |  | E |  | High | 1 - High | 268515, 268555 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD | D#73731 - REF Business Cutover - Correct Constant Entry to remove 0490 | 27 - Resolved | EWM |  | E |  | Low | 1 - High | [5 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD | D#73733 - Days of Skip Upload Program Fail - Timeout Issue | 27 - Resolved | EWM |  | E |  | Medium | 3 - Low | [5 empty] | Vaibhav | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73740 - Enhancement: "Full Pallet Qty" field to be added to Outbound Truckboard | 06 - Dev Completed | EWM |  | E |  | Medium | 1 - High | 268809 |  |  |  |  | Mayuri/Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0009 | D#73742 - Putaway is ignoring height limitation on locations and over-directing HU's to bins. | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268441, 268506 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDD010778 | D#73769 - Insite - Movement 311 to Insite | 27 - Resolved | EWM |  | I |  | Medium | 3 - Low | [5 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD010778 | D#73770 - Insite-Modify CHG/CHG logic for 323 to NID and NIR | 13 - Deferred | EWM |  | I |  | Medium | 3 - Low | [5 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD10778 | D#73781 - Insite - Hu splits do not report correct line item balance to Insite | 06 - Dev Completed | EWM |  | I |  | Medium | 1 - High | 268481, 268472 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDD10778 | D#73785 - Insite - Picking same item/same batch is not updating HU balance correctly to Insite | 27 - Resolved | EWM |  | I |  | Medium | 1 - High | 268481, 268472 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73814 - Enhancement: Truckboard Update - Pick Status | 13 - Deferred | EWM |  | E |  | Low | 3 - Low | [5 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0009 | D#73817 - Putawy proving locations without enough height for HU's | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268506 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73818 - During PGI it is checking quality hold but only for the product. It is not looking at the expiration date | 06 - Dev Completed | EWM |  | E |  | Medium | 1 - High | 268509, 268575 | [10 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDD0050 | D#73825 - Kaleris Integration - Inbound WT for empty trailers not triggering in EWM | 27 - Resolved | EWM |  | I |  | Medium | 3 - Low | 268485 |  |  |  |  | Kiran | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0035 | D#73826 - IBD creation - SPED failure for zero quantity item | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268496 |  |  |  |  | Pratik M | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD010778 | D#73830 - InSite EWM to Insite inbound interface sending multiple inbound truck verifies | 13 - Deferred | EWM |  | E |  | Medium | 3 - Low | [5 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0014 | D#73845 - For DS products case and layer coming as zero on RF | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268538 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#73853 - Open Loading Qty on truckboard shows 0 | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268548 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0014 | D#73856 - When taking a pallet out of staging, Pre-Bilt is asking for the pallet to go to Outbound Staging. | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268806 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0038, EDD0050 | D#73860 - Having trouble releasing waves for picking - not creating replen for stock types OA and EI | 06 - Dev Completed | EWM |  | E |  | Medium | 1 - High | 269351,269474,269588,270198,270242 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-16 |  | 2024-10-16 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0019 | D#73872 - Can not load outbound trailers with different disposition codes | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268534 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0020 | D#73884 - Load Sequence Issue - Skipping Sequence | 27 - Resolved | EWM |  | E |  | High | 1 - High | 268540 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#73905 - Layer Wave release creating WO with WOCR CS0R, Ideally CS0R is for resume WO which is applicable for case picking. | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268570 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDDXXXX | D#73906 - Kaleris SCAC Mismatch Development | 06 - Dev Completed | EWM |  | I |  | Medium | 3 - Low | [5 empty] | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0014 | D#73908 - Restrict tcode ZEWM_CB_HOLD access by warehouse | 13 - Deferred | EWM |  | E |  | Medium | 3 - Low | [5 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0053 | D#73914 - Layer Pick Wave with 50+ items | 06 - Dev Completed | EWM |  | E |  | Very High | 1 - High | 268515, 268555, 268754 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0020 | D#73922 - Sequencing Issue - LTL TU (Load Balancing) | 06 - Dev Completed | EWM |  | E |  | Very High | 1 - High | 268713, 268842 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0038, EDD0011, EDD0009 | D#73933 - RF Line Retrieval Issues: asking to retrieve multiple pallets (too tall), CHHU error, error when splitting | 06 - Dev Completed | EWM |  | E |  | High | 1 - High | 268729, 268755, 268765, 268756 |  |  |  |  | Neha/Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#73935 - Load Plan - No load plan for any HUs, load plan is green in truckboard | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268634 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0019, EDD0020 | D#73936 - Load Plan Sequence | 06 - Dev Completed | EWM |  | E |  | High | 1 - High | 268792, 268895 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0038 | D#73949 - Replens not being driven once picking wave released and avail quantity is in reserve | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268583 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDDXXXX | D#73982 - Inventory Cycle Count Lockup | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268686 |  |  |  |  | Kiran | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0008 | D#74011 - RMA Not Showing up | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 268733 |  |  |  |  | Vaibhav | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0019 | D#74137 - LTL Can not be loaded | 27 - Resolved | EWM |  | E |  | Medium | 1 - High | 268701 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#74180 - Weight in truckboard for LTLs | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268809, 268826 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0035 | D#74242 - SPED failure due to incorret HU Ststus | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 268795 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0086 | D#74243 - Fix and thoroughly test custom program that updates sloc on STO | 27 - Resolved | EWM |  | E |  | Low | 2 - Medium | 268876 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0010 | D#74244 - Need section check when moving partial pallets. | 06 - Dev Completed | EWM |  | E |  | Medium | 1 - High | 268766 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#74301 - Assign TU Priority & User is not site-specific but should be | 27 - Resolved | EWM |  | E |  | High | 1 - High | 268796 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | EDD0010 | 6700 - Putaway RF Execution | 05 - Dev On-Hold | EWM |  | E |  | Medium |  | 269459 |  |  |  |  | Veereshravi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-05 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD006, EDD0011 | D#74346 - Speed of System - Prebilt & Friori speed | 27 - Resolved | EWM |  | E |  | High |  | 269328, 269298, 269401 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-28 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD10778 | D#74417 - Insite - Block movement for indirect material 599216 from feeding insite | 13 - Deferred | EWM |  | I |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | IDD10778 | D#74419 - Insite - Duplicate key to Insite on repack of mixed HU's | 13 - Deferred | EWM |  | I |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0006 | D#74612 - Inbound Critical Flag | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269185, 269328 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-21 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0036 | D#74615 - Crossdock was selecting wrong outbound delivery line item | 27 - Resolved | EWM |  | E |  | Medium |  | 266319 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-02 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDDXXXX | D#74623 - Pick quantities are less than a full case | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269100 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-06 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#74624 - Enhancement - Critical in warehouse at pickline, but system is showing zero | 06 - Dev Completed | EWM |  | E |  | Medium | [6 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDD0047 | D#74627 - Kaleris - Live Trailers are not showing Docked in PINC | 27 - Resolved | EWM |  | I |  | Medium |  | 269098, 269157 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#74628 - Truck Board Yard Sections Missing | 27 - Resolved | EWM |  | E |  | Medium |  | 269180 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-09 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDDXXXX | D#74629 - Kaleris - Truckboard - Trailer Assignment in YardMgmt button for pre-populated trailer number | 27 - Resolved | EWM |  | I |  | Medium | 2 - Medium | [5 empty] | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-04 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | IDDXXXX | D#74634 - Kaleris - EWM > YMS, change needed for interface -1 | 27 - Resolved | EWM |  | I |  | Medium |  | 269106, 269157, 269183 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-05 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 19 | EDD0035 | D#74638 - V51VP error in SPED processing | 27 - Resolved | EWM |  | E |  | Medium |  | 267825 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0006, EDD0011 | D#74641 - Can Not Assign LTO to TU in Truckboard | 27 - Resolved | EWM |  | E |  | High |  | 269081 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0053 | D#74645 - Slotting Program - Fiori Time Out Issue | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 269090 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-07 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#74662 - 2000010508 - WO for CSOR task issue | 27 - Resolved | EWM |  | E |  | Medium |  | 269127 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0005 | D#74675 - Enhancement - ARIBA Purchase Orders not filtered in the Inbound Scheduling Report | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269312 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-20 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0038 | D#74676 - Wave Release ABAP Dump in WWP -Dry | 27 - Resolved | EWM |  | E |  | Medium |  | 269083 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-07 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0014 | D#74681 - LTO not getting countback after case picking | 27 - Resolved | EWM |  | E |  | Medium |  | 269137 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-06 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0045 | D#74687 - PI counting dump ABAP Error | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 269138 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0037 | D#74688 - Posting Change - Stock Type QT to AV Batch Job Error | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 269139 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-09 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0021 | D#74722 - Quality Hold - Read only Exact Date in Start Date if End Date is blank | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 269166 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-14 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0020 | D#74726 - Load Balancing - Defect with Load Planning | 27 - Resolved | EWM |  | E |  | Medium |  | 269167 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [8 empty] | 2024-08-13 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0011 | 6871 - Split Criticals - CSPT to CS01 | 06 - Dev Completed | EWM |  | E |  | High |  | 269952 |  |  |  |  | Mayuri |  |  | 2024-09-11 | 2024-09-11 |  | 00 - FUT Not Started | [6 empty] | 2024-09-23 | [20 empty] | 6871 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0019 | 6894 - RF TU indication - LTL & Multi-stop Loads | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269900 |  |  |  |  | Sneha |  |  | 2024-09-09 | 2024-09-09 | 2024-09-09 | 00 - FUT Not Started | [6 empty] | 2024-09-13 |  | 2024-09-13 | [18 empty] | 6894 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0007 | 5190 - OS&D - Receival of product on different BOL + QT | 19- FUT in Progress | EWM |  | E |  | Medium |  | 270414 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-21 |  | 2024-10-21 | [18 empty] | 5190 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD | 5238 - Autoshuttle Process - Direct outbound delivery | 01- FSD not received | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | RDD0127 | 5955 - Y-Stock Reports | 19- FUT in Progress | EWM |  | R |  | Medium |  | 270672, 270490 |  |  |  |  | Neha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-18 |  | 2024-10-18 | [18 empty] | 5955 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | IDD010778 | 6909 - Insite Enhancements | 19- FUT in Progress | EWM |  | I |  | High |  | 270495 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-18 | [20 empty] | 6909 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0010 | 6906 - Deconsolidation | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269729 |  |  |  |  | Sudhanshu |  |  |  | 2024-09-06 | 2024-09-06 | 00 - FUT Not Started | [6 empty] | 2024-09-12 |  | 2024-09-12 | [18 empty] | 6906 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | IDD0040 | 6905 - Autoshuttle from Matrics to EWM | 19- FUT in Progress | EWM |  | I |  | Medium |  | 269477, 270717 |  |  |  |  | Shiny/Raja/Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0053 | 6908 - Slotting Program | 06 - Dev Completed | EWM |  | E |  | High |  | 270242 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [27 empty] | 6908 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0013 | 7147 - Divert to case pick line assuming product is already there | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269895 |  |  |  |  | Neha |  |  | 2024-09-10 | 2024-09-10 | 2024-09-10 | 00 - FUT Not Started | [6 empty] | 2024-09-17 | [20 empty] | 7147 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0010/EDD0019/EDD0038/EDD0014 | 7154 - HUs stuck on resources | 06 - Dev Completed | EWM |  | E |  | Medium |  | 270033,270090,270273 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-25 |  | 2024-09-25 | [18 empty] | 7154 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | IDD0051 | 6895 - YMS Enhancements - Exception Scenarios | 05 - Dev On-Hold | EWM |  | I |  | Medium |  | 267872 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [27 empty] | 6895 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0014 | D#74727 - Incorrect Bin Scan Dumps or ABAP Error from RF | 27 - Resolved | EWM |  | E |  | Medium |  | 269165 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-09 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0010 | D#74730 - Enhancement: Deconsolidation process not flexible enough for production. | 13 - Deferred | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0039, EDD0011 | D#74761 - Pick Task Handling Indicators not sorted to PSHU pick sequence | 27 - Resolved | EWM |  | E |  | Medium |  | 269322, 269806 |  |  |  |  | Sneha/Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-11 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0011 | D#74763 - Truckboard Stoplights and Totals: Trailer is 100% loaded. Flag is Green. TU: 2090707240 | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269401, 269556, 270214 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-01 |  | 2024-10-01 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0014 | D#74767 - Task Conversion to CS0R Not Happening | 27 - Resolved | EWM |  | E |  | Medium |  | 269371 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-22 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD | D#74776 - LTL Shipments | 27 - Resolved | EWM |  | E |  | Medium |  | 269266 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-14 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0014 | D#74806 - Error on Loading during for LTL Load | 27 - Resolved | EWM |  | E |  | Medium |  | 269285 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-13 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD | D#74809 - Inbounds Docking and Undocking Several Times During Unloading | 27 - Resolved | EWM |  | E |  | Medium |  | 269268 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-13 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0006 | D#74812 - Kaleris - FLIP IB to OB button not working in EWM | 27 - Resolved | EWM |  | E |  | Medium |  | 269300 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-15 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0005 | D#74820 - Inbound Scheduling Report Runtime Error | 27 - Resolved | EWM |  | E |  | Medium |  | 269294 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-13 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#74854 - CSPT not converting to CS01 | 27 - Resolved | EWM |  | E |  | Medium |  | 269266 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-14 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0014 | D#74882 - Cycle Counter PI Documents not auto posting | 06 - Dev Completed | EWM |  | F |  | Medium |  | 267868 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0006 | D#74923 - Arriving Inbound Trailers from Ref are causing issues. | 27 - Resolved | EWM |  | E |  | Medium |  | 269484 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-26 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0019 | D#74935 - Full Pick Denial Not Working on Replen | 27 - Resolved | EWM |  | E |  | Medium |  | 269543 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-27 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0008 | D#74947 - GI failing on sales orders with YTAN and YTAQ item category | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269602 |  |  |  |  | Neha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-03 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0007 | D#74965 - Inbound dump error when doing new HU | 27 - Resolved | EWM |  | E |  | Medium |  | 269393 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-21 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 17 | EDD0011 | D#74988 - Unreleased wave not showing on truckboard | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269552 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-26 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0011 | D#74992 - OB Truckboard Wave Release Indicator | 27 - Resolved | EWM |  | E |  | Medium |  | 269401 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-23 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0021 | D#75004 - Springfield_5418_HUs are not updated in the Quality Hold | 27 - Resolved | EWM |  | E |  | Medium |  | 269491 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-12 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | ITC Defect | Sprint 17 | EDD0021 | D#75123 - Q-Hold HU's not adding correctly | 27 - Resolved | EWM |  | E |  | Medium |  | 269491 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-08-29 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | ITC Defect | Sprint 17 | IDD0047 | D#75162 - Kaleris: Inbound STO TU not reached to Springfield kaleris | 27 - Resolved | EWM |  | I |  | Medium |  | 265962 |  |  |  |  | Jubaraj | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-11 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | ITC Defect | Sprint 17 | EDD0053 | D#75208 - Slotting program showing incorrect slotting values | 27 - Resolved | EWM |  | E |  | Medium | [6 empty] | Jubaraj | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0021 | D#75294 - Quality Hold Node not updating Changed by field when Hold ID is updated | 27 - Resolved | EWM |  | E |  | Medium |  | 269491 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-12 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | FDD0017, FDD0018 | D#75360 - Can print outbound paperwork, but shipment will not GI. | 27 - Resolved | EWM |  | F |  | Medium |  | 269933 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-13 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 17 | EDD0009 | D#75387 - Inbound pallets to the pickline are causing issues | 27 - Resolved | EWM |  | E |  | Medium |  | 269959 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-13 | [22 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0062 | 6079 - Dispatch of Notification for the pallets from EWM | 06 - Dev Completed | EWM |  | I |  | Medium |  | 269878, 269712 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-25 | [20 empty] | 6079 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | EDD0123 | 6701 - System Board id Internal Movement | 06 - Dev Completed | EWM |  | I |  | Medium |  | 269035 |  |  |  |  | Veereshravi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-05 |  | 2024-09-27 | [18 empty] | 6701 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | EDD0007 | 6702 - Enhance Sort (deconsolidate) functionality for mixed pallets for putaway | 05 - Dev On-Hold | EWM |  | E |  | Medium |  | 269587 |  |  |  |  | Ramya | [5 empty] | 00 - FUT Not Started | [27 empty] | 6702 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0065 | 6416 - Inventory Sync Response - INV002 | 06 - Dev Completed | EWM |  | I |  | Medium |  | 269620 |  |  |  |  | Rohit | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-16 |  | 2024-09-13 | 2024-09-02 |  | 2024-09-02 | [15 empty] | 6416 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0073 | 6843 - WCS Inventory Status Update Confirmation | 06 - Dev Completed | EWM |  | I |  | Medium |  | 264720 |  |  |  |  | Vaibhav | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-10 |  | 2024-09-10 | 2024-09-03 |  | 2024-09-03 | [15 empty] | 6843 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0063 | 6869 - Loop logic for trigger validation | 06 - Dev Completed | EWM |  | I |  | Medium |  | 268759 |  |  |  |  | Kiran | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-13 |  | 2024-09-25 | 2024-09-05 |  | 2024-09-05 | [15 empty] | 6869 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0055 | 6889 - Mapping of Item keep low flag | 02- FSD received / Dev not Started | EWM |  | I |  | Medium |  | 267552 | [10 empty] | 00 - FUT Not Started | [27 empty] | 6889 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 18 | IDD0056 | 6904 - Map system board id INB001 | 06 - Dev Completed | EWM |  | I |  | Medium |  | 267373 |  |  |  |  | Veereshravi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-09 |  | 2024-09-23 | 2024-09-03 |  | 2024-09-03 | [15 empty] | 6904 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0019 | D#75451: SP18:US#6894:RF TU indication - LTL & Multi-stop Loads - User Story Move to P | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 269900 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-16 |  | 2024-09-16 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0013 | D#75508: SP18:US#7147: Divert to case pick line assuming product - Move to P | 06 - Dev Completed | EWM |  | E |  | Medium |  | 269895,270076 |  |  |  |  | Neha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-19 |  | 2024-09-19 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 18 | EDD0020 | US#7155: EDD0020: Pick Pallets Height for Load Plan | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 270031 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-18 |  | 2024-09-18 | [18 empty] | 7155 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 18 | EDD0020 | D#75509: US#7155: EDD0020: Pick Pallets Height for Load Plan | 06 - Dev Completed | EWM |  | E |  | Medium |  | 270031 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-18 |  | 2024-09-18 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 19 | EDD0006 | D#75573 - Product setup showing as green in inbound truckboard when packspec and mat1 have not been setup for item. | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 270207 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-26 |  | 2024-09-26 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 18 | EDD0011 | D#75606 - SP18 User Story 6871 Auto Split during Release for criticals - CSPT to CS01 - Move to P | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 269952 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-24 |  | 2024-09-24 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | UAT Defect | Sprint 19 | EDD0007 | D#75607 - New HU not getting displayed once the Yes button is clicked for the message 'Product not on delivery Do you want to proceed' | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 270290 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-27 |  | 2024-09-27 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 18 | EDD0010/EDD0019/EDD0038/EDD0014 | D#75608: SP18:US#7154: Defect for HU Stuck on Resource User Story | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 270033,270090,270273 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-09-25 |  | 2024-09-25 | [18 empty] | 7154 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 19 | EDD0019 | D#75671 - loose cases on the resource / loose cases in staging | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 270394 |  |  |  |  | Sudhanshu | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-08 |  | 2024-10-08 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 19 | EDD0020 | D#75675 - Load Sequencing Error - Pallet on IB Staging skipped sequence 9 | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | [5 empty] | Sneha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect | Sprint 19 | EDD0021 | D#75775 - Q1 is not being applied to Instransit items by code date. | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 270612 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-15 |  | 2024-10-15 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0008 | D#75173 - Queue Failure CARR Exception code not working | 27 - Resolved | EWM |  | E |  | Medium | 2 - Medium | 267825 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-16 |  | 2024-10-16 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | Hypercare Defect (Change) | Sprint 19 | EDD0038/ EDD0011 | D#75021 - Enhancement-PSHU Not Found Happening for Multiple Waves | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 269703,269798,269924,270183,270210,270356,270440 |  |  |  |  | Sneha, Neha, Raja, Mayuri | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-11 |  | 2024-10-11 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0006 | 7294 - OS&D - Default CARR for every queue failure on Inbound | 06 - Dev Completed | EWM |  | E |  | Medium | 1 - High | 270304 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-02 |  | 2024-10-02 | [18 empty] | 7294 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0014 | 6885 - Inventory Cycle Count Enhancements (Full pick denial) | 19- FUT in Progress | EWM |  | E |  | Medium |  | 270521, 270522 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-21 | [20 empty] | 6885 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD | 7165 - Missing ZCUS | 01- FSD not received | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [27 empty] | 7165 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0019 | 7156 - Load Denial Screen for Lost HUs | 19- FUT in Progress | EWM |  | E |  | Medium |  | 270413 |  |  |  |  | Raja | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-15 |  | 2024-10-15 | [18 empty] | 7156 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 19 | EDD0003 | 7000 - Add Keep Low Flag to Warehouse Product View | 02- FSD received / Dev not Started | EWM |  | E |  | Medium | [12 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 19 | EDD0123 | 7143 - Enhancement - RF Initiated Bin to Bin from Conventional to Automation Infeed Lane | 04 - Dev in progress | EWM |  | E |  | Medium | [6 empty] | Veereshravi | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-08 |  | 2024-10-08 | [18 empty] | 7143 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | Supernova | WRICEF | Sprint 19 | EDD13596 | 7164 - Enhancement to Stop Confirmation of Induction Tasks from the WH Monitor | 02- FSD received / Dev not Started | EWM |  | E |  | Medium | [6 empty] | Veereshravi | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0035 | 7533 - Inbound Autoshuttle (SPED) | 19- FUT in Progress | EWM |  | E |  | High | 2 - Medium | 270717 |  |  |  |  | Sneha | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-22 |  | 2024-10-22 | [20 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDDXXXX | Restrict tcode ZEWM_CB_HOLD access by warehouse | 01- FSD not received | EWM |  | E |  | Medium | [6 empty] | Neha | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0013 | 7282 - Springfield case pick config | 06 - Dev Completed | EWM |  | E |  | Medium | 2 - Medium | 270666 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [6 empty] | 2024-10-16 |  | 2024-10-16 | [18 empty] | 7282 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 19 | EDD0007 | 7428 - Change Batch Process w/ New HU Creation Taking Too Long | 03 - Waiting for FSD walk-through | EWM |  | E |  | High | 2 - Medium | [5 empty] | Sudhanshu | [5 empty] | 00 - FUT Not Started | [27 empty] | 7428 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | User Story | Sprint 20 | EDD0014/EDD0010 | 7246 - Putback Queue Location Visibility | 04 - Dev in progress | EWM |  | E |  | Medium | 2 - Medium | 270721 |  |  |  |  | Raja |  |  |  | 2024-10-15 | 2024-10-15 | 00 - FUT Not Started | [27 empty] | 7246 |  | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | UAT Defect | Sprint 19 | EDD00001 | D#75747 - Outbound Scheduling Report Error with Dates | 19- FUT in Progress | EWM |  | E |  | Medium |  | 270555,270757 |  |  |  |  | Shiny | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10
EWM | EWM NA Phase 4 | UAT Defect | Sprint 20 | EDD0006 | D#76357 - SAP ABAP Error while clicking on 'Assign Door' button when no line items are selected | 27 - Resolved | EWM |  | E |  | Medium |  | 270955 |  |  |  |  | Mayuri | [5 empty] | 00 - FUT Not Started | [29 empty] | Not Started | Item | sites/IBMDevelopmentTracker/Lists/Global WRICEF Tracker Ver 10